ATC/AFC/TRM/CBM/TTC/TFC/ETC Standard Development Plan

	Action
	ATC/AFC
	TRM
	CBM
	TTC/TFC
	ETC

	
	
	
	
	
	

	Send to NAESB
	
	3/14
	
	
	

	Comments due back
	March 16
	
	
	
	

	Comments to drafting team
	March 21
	
	
	
	

	Webex
	March 23

Assign comments
	March 23 Finalize
	
	
	

	Posting 30 days
	
	4/1
	
	
	

	Meeting Birmingham at Southern Co
	4/11-12

Comments review and revisions
	
	4/11-12

draft
	4/11-12

draft
	4/11-12

draft

	
	
	
	
	
	

	Meeting Houston at NAESB
	4/23

NAESB review
	
	
	
	

	Meeting Houston at NAESB 
	
	
	4/24-25

complete
	4/24-25
	4/24-25

	Comments due back
	
	5/2
	
	
	

	Webex with NAESB
	5/3
	5/3
	5/3 
	5/3
	5/3

	Comments to drafting team
	
	57
	
	
	

	Meeting

Atlanta
	5/15-17
Finalize, Review with NAESB
	5/15-17
Finalize, Review with NAESB
	5/15-17
Finalize, Review with NAESB
	5/15-17
Finalize, Review with NAESB
	5/15-17
Finalize, Review with NAESB

	Posting 45 days
	5/23
	5/23
	5/23
	5/23
	5/23

	Meeting (tentative)
Chicago/St. Louis
	6/12-13
	6/12-13
	6/12-13
	6/12-13
	6/12-13

	Comments due back
	7/9
	7/9
	7/9
	7/9
	7/9

	Comments to drafting team
	7/12
	7/12
	7/12
	7/12
	7/12

	Webex
	7/13
	7/13
	7/13
	7/13
	7/13

	Meeting 
Vancouver / Portland / San Francisco/ Sacramento
	7/16 - 19

Prepare Responses, review w/  NAESB

finalize changes
	7/16 - 19

Prepare Responses, review w/ NAESB

finalize changes
	7/16 - 19

Prepare Responses, review w/ NAESB

finalize changes
	7/16 - 19

Prepare Responses, review w/ NAESB

finalize changes
	7/16 - 19

Prepare Responses, review w/ NAESB

finalize changes

	Post 30 days
	7/23
	7/23
	7/23
	7/23
	7/23

	Comments due back
	8/22
	8/22
	8/22
	8/22
	8/22

	Comments to drafting team
	8/24
	8/24
	8/24
	8/24
	8/24

	Meeting

Denver / Salt Lake
	8/27-30

Prepare responses and revisions
	8/27-30

Prepare responses and revisions
	8/27-30

Prepare responses and revisions
	8/27-30

Prepare responses and revisions
	8/27-30

Prepare responses and revisions

	Posting for ballot
	9/6
	9/6
	9/6
	9/6
	9/6

	Meeting
	9/18-20
Review comments/revise
	9/18-20
Review comments/revise
	9/18-20
Review comments/revise
	9/18-20
Review comments/revise
	9/18-20
Review comments/revise

	Post recirc ballot
	9/21
	9/21
	9/21
	9/21
	9/21

	
	
	
	
	
	

	Send result to Board
	10/1
	10/1
	10/1
	10/1
	10/1


Meeting Details

April 11 - 12 

Birmingham  

  8a - 5p both days
  Southern Company
April 23 

Houston  

10a - 5p

  NAESB offices
April 24 - 25 

Houston     

  9a - 5p both days
  NAESB offices
May 3rd 

webex  

11a - 5pm

May 15 - 17 

Atlanta 

  8a - 5p all 3 days  
  Georgia Transmission Corporation
June 12-13 

Chicago

  8a – 5p both days
  t.b.d.  (tentative)
July 16 

Vancouver

noon to 5p 

  t.b.d.

July 17 - 19 

Vancouver 

 8a - 5p all 3 days
  t.b.d

Vancouver/San Francisco/Portland/Sacramento

Aug 27

Denver/Salt Lake
noon to 5p

  t.b.d.
Aug 28 - 30 

Denver/Salt Lake
8a – 5p both days
  t.b.d.  

Sep 18 - 20  

D.C. / Baltimore
8a – 5p all 3 days
  t.b.d.
