| NORTH AMERICAN ENERGY STANDARDS BOARD 2007 ANNUAL PLAN for the RETAIL GAS and ELECTRIC QUADRANTS1 Approved by the Board of Directors on September 27, 2007 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Item Number & Description |  |  |  |  | Completion2 | Assignment |
| 1 |  | Billing & Payment |  |  |  |  |  |  |
|  |  |  | Develop additional model business practices for reversal and reissue, transformer loss factors, budget billing and payment plans, and missed bill windows Status: Complete |  |  |  | 1st Q 2007 | IR |
| 2 |  | Electronic Retail Billing. |  |  |  |  |  |  |
|  |  |  | Develop Technical Electronic Implementation Standards – Electronic Retail Billing Status: Underway |  |  |  | 2nd Q 2007 | TEIS |
| 3 | Customer Enrollment, Drop and Account Information Change |  |  |  |  |  |  |  |
|  | a. |  | Develop practices for submitting and receiving, processing and fulfilling a customer’s request to enroll with or leave a supplier (including suppliers dropping customers) and for maintaining current customer account information, and for notifying affected parties. |  |  |  | 2nd Q 2007 | BPS |
|  |  |  | i) |  |  | Customer Enrollment Status: Complete | 2nd Q 2007 | BPS |
|  |  |  | ii) |  |  | Customer Drop Status: Complete | 1st Q 2007 | BPS |
|  |  |  | iii) |  |  | Account Information Change Status: Complete | 2nd Q 2007 | BPS |
|  | b. |  | Develop information requirements for submitting and receiving, processing and fulfilling a customer’s request to enroll with or leave a supplier (including suppliers dropping customers) and for maintaining current customer account information, and for notifying affected parties. Status: Underway |  |  |  | 3rd Q 2007 | IR |
|  | c. |  | Develop Technical Electronic Implementation Standards – Customer Enrollment, Drop and Account Information Change, Status: Not Started |  |  |  | 4th Q 2007 | TEIS |
| 4 | Customer Enrollment, Drop and Account Information Change Using a Registration Agent |  |  |  |  |  |  |  |
|  |  |  | Develop practices when using a Registration Agent for submitting and receiving, processing and fulfilling a Customer’s request to enroll with or leave a Supplier (including Suppliers dropping Customers) and for maintaining current Customer account information, and for notifying affected parties. |  |  |  |  |  |
|  |  |  | i) |  | Customer Enrollment Status: Underway |  | 3rd Q 2007 | Texas Task Force/ BPS |
|  |  |  | ii) |  | Customer Drop Status: Not Started |  | 4th Q 2007 | Texas Task Force/ BPS |
|  |  |  | iii) |  | Account Information Change Status: Not Started |  | 1st Q 2008 | Texas Task Force/ BPS |
| 5 | Customer Information |  |  |  |  |  |  |  |
|  |  |  | Develop additional model business practices for Customer Information Status: Underway |  |  |  | 2008 | BPS |
| 6 | Customer Inquiries |  |  |  |  |  |  |  |
|  |  |  | Develop procedures for responding to customer inquiries directed to Distributors and/or Suppliers and for notification of the other party. Status: Not Started. Delayed to 2008 for completion because the registration agent model is separate from customer enrollments. |  |  |  | 2008 | BPS |
| 7 | Prepare a joint analysis with the WGQ for AS2 and AS3 protocols as compared to the NAESB IET. Status: Underway |  |  |  |  |  | 4th Q 2007 | TEIS & WGQ EDM |
| 8 | Develop NAESB Certification checklist criteria for Retail Quadrants to be used in the NAESB Certification Program. Status: Not Started |  |  |  |  |  | TBD | TEIS |
| 9 | Address issues raised in the Department of Energy’s Sandia National Laboratories on NAESB technical standards and respond to the surety assessment findings and recommendations. Status: Underway |  |  |  |  |  | 4th Q 2007 | BPS/TEIS |
| 10 | Consider and develop as needed model business practices to support Gas Design Day Forecast Status: Not Started. A reach out to the SGA and AGA for subject matter experts will be undertaken first, before the group is populated. |  |  |  |  |  | TBD | RGQ - Gas Design Day Task Force |
| 11 | Review and develop needed model business practices for a standardized method for quantifying benefits, savings, cost avoidance and/or the reduction in energy demand and usage derived from the implementation of demand side management and energy efficiency programs. This effort will include demand side response, energy efficiency programs and metering, including the 'curtailment service provider' program. Status: Underway |  |  |  |  |  | 2008 | Joint WEQ/Retail DSM Subcommittee |
| Program of Standards Maintenance & Fully Staffed Standards Work2 |  |  |  |  |  |  |  |  |
|  |  | Business Practice Requests |  |  |  |  | Ongoing | Assigned by the EC3 |
|  |  | Information Requirements and Technical Mapping of Business Practices |  |  |  |  | Ongoing | Assigned by the EC4 |
|  |  | Ongoing Interpretations for Clarifying Language Ambiguities |  |  |  |  | Ongoing | Assigned by the EC4 |
|  |  | Ongoing Maintenance of Code Values and Other Technical Matters |  |  |  |  | Ongoing | Assigned by the EC4 |
|  |  | Ongoing Development and Maintenance of Definitions |  |  |  |  | Ongoing | Glossary |
| Provisional Activities |  |  |  |  |  |  |  |  |
|  |  | Joint Effort: |  |  |  |  |  |  |
|  |  |  |  | Supplier Certification: Develop practices for Distribution Companies to register/certify new Suppliers when they seek to begin doing business in the Distribution Company’s service area. |  |  |  |  |
|  |  |  |  | Modify TPA as necessary. |  |  |  |  |
|  |  |  |  | Review security standards as may be deemed necessary, such as Public Key Infrastructure (PKI). |  |  |  |  |
|  |  |  |  | Review existing body of model business practices for consistency and develop or modify model business practices as needed. |  |  |  |  |
|  |  |  |  | Review existing body of model business practices for applicability to registration agents and develop model business practices as needed. |  |  |  |  |
|  |  | Retail Electric Quadrant Effort Only: |  |  |  |  |  |  |
|  |  |  |  | Retail Meter Data Validation, Editing & Estimating: Develop procedures for insuring the integrity and validity of retail customer metering data that is needed by utilities and suppliers for billing, etc. Issues related to unbundled or competitive metering are not to be considered. |  |  |  |  |
|  |  |  |  | Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market. Note: will need to be coordinated with the WEQ for the REQ. |  |  |  |  |
|  |  | Retail Gas Quadrant Effort Only: |  |  |  |  |  |  |
|  |  |  |  | Examine Wholesale Gas Quadrant Non-EDM Standards for applicability to retail business practices. |  |  |  |  |
|  |  |  |  | Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market. |  |  |  |  |

Retail Electric & Retail Gas

Quadrant Executive Committees

(REQ and RGQ ECs)

Business Practices Subcommittee (BPS)

Contracts Subcommittee (dormant)

Glossary Subcommittee

Information Requirements Subcommittee (IR)

Technical Electronic

Implementation Subcommittee (TEIS)

Model Business

Practice

Development

Task Forces & Working Groups5

Technical

Standards

Development

Joint Retail/WEQ DSM-EE Subcommittee

NAESB Retail Subcommittee Leadership:

Executive Committee:  Mike Novak, Chair (RGQ), Ruth Kiselewich, Chair (REQ)

Business Practices Subcommittee:  Phil Precht (RGQ), Mary Edwards and Dan Jones (REQ)

Information Requirements Subcommittee: Jennifer Teel (REQ)

Technical Electronic Implementation Subcommittee: Dan Rothfuss (RGQ)

Glossary Subcommittee:  Don Sytsma (RGQ), Mary Edwards and Patrick Eynon (REQ)

DSM-EE Subcommittee: Ruth Kiselewich, David Koogler (REQ), Roy True (WEQ), Paul Wattles (WEQ)

End Notes:

1 As outlined in the NAESB Bylaws, the REQ and RGQ will also address requests submitted by members and assigned to the REQ and RGQ through the Triage Process.

2 Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed so as to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.

3 This work is considered routine maintenance and thus the items are not separately numbered.

4 The REQ and RGQ ECs will assign maintenance efforts on a request by request basis.

5 The ECs and the subcommittees can create task forces and working groups to support their development activities for development of model business practices and technical standards.

1.	Gas Design Day Forecast

Submitted by Ralph Cleveland, Senior Vice President | Engineering and Operations, AGL Resources

From: Ralph Cleveland [mailto:rcleve@aglresources.com]

Sent: Tuesday, October 10, 2006 5:13 PM

To: naesb@naesb.org

Subject: Gas Design Day Forecasting Standard

The following are the concepts around which it would be helpful to have an industry standard as to reasonable and acceptable modeling or methodology approach.  I’m not sure how a proposal is usually structured, but I wanted to get this to NAESB today.  This should be a good start.  AGA and SGA have done some work through surveys and conferences to identify industry practice.  For regulatory reasons, I think they have avoided attempting to say that there are established “best practices”.  We have some AGA/SGA survey results, if you would like to see them.  If this is not what you were looking for, please let me know.

1.	Number of years history considered in arriving at the design temperature (coldest in X years)

2.	Acceptable independent variable besides same day temperature used in analysis (prior day temp, wind speed, etc)

3.	Reasonable historical load / temperature analysis approach used to forecast future design (regression analysis, average load per HDD on cold days, etc)

4.	Approach at removing outlier data from historical data sets

5.	Acceptable R^2, MAPE or other statistical measure or forecast accuracy

6.	Method for accessing potential design day forecast error (capacity reserve margin, forecast adder, etc)

7.	Methodology to project design period load shape (multiple design days, historic design period temperatures, statistical approach)

8.	Assumptions associated with on-system facility derate or pipeline capacity proration on design day.

RESOLUTION 11-15-06:  Added to 2007 Annual Plan-- Reach out to SGA and AGA for subject matter experts will be undertaken.

2.	Northeast Regional Best Practices

Submitted by Phil Precht, BG&E

Excerpt from “Restructuring Today”:  A major effort in that direction is a push to stimulate and activate pro-markets members of the legislature at a two day meeting set for  Wilmington Oct 24-25 at the Doubletree Hotel. NEMA is behind the move. It's relying on pro-markets members of legislatures in Delaware, Pennsylvania and possibly Connecticut for a leadership round table and regulatory workshop to meet in Wilmington. James Lester of the Delaware PSC is a key speaker along with James Cawley who is the vice chair in Harrisburg. Several state legislators are to speak. Craig Goodman reports that business backers are happy to have marketers coming into Delaware to compete to supply the market. He's invited commissioners and staff from Delaware, Pennsylvania, New York and Connecticut to point out the best practices in the region. One subject of course will be the successes in New York and how to apply those best practices to other states.  A major goal is not just copying New York's success but making the progress regional.  Goodman thinks that would drive prices in the region down, lower the acquisition costs and bring economies of scale to the marketplace. Day one right now is best practices and day two is how to get there (implementation).

RESOLUTION 11-15-06:  Not added to 2007 Annual Plan at this time – outreach to Craig Goodman first for feasibility.

3.	Demand Side Response

Submitted by George Behr, Energy Services Group

PJM is discussing demand side response and metering.  They have a 'curtailment service provider' program that might benefit from NAESB standards. There are both wholesale and retail implications.

RESOLUTION 11-15-06:  Combined with item 4 below.

4.	Standardized Method for Quantifying Benefits, Savings, Cost Avoidance and/or the Reduction in Energy Demand Derived From the Implementation of Demand Side Management and Energy Efficiency Programs

Submitted by Carl Wilkins, Advanced Energy

LETTER:

Dear Ms. McQuade:  Attached is a request for initiation of a NAESB business practice standard as described in your September 11, 2006, memo.  We were advised by one of your board members, Mr. David Koogler with Dominion Power, to submit a request.  Mr. Koogler was present when we gave our annual report to the N.C. Utilities Commission.  He took note that we were challenged by one of the Commissioners to quantify more of the benefits that North Carolina and other states were enjoying as result of the work we do with energy utilization and market transformation.  Advanced Energy is an independent non-profit that was chartered by the N.C. Utilities Commission in 1980 to work with electric utilities, in part, to develop and demand side management (DSM) and energy efficiency (EE) programs.  Since 1980 Advanced Energy has been doing public benefits work to enhance how North Carolina businesses and individuals use energy.  Recently we have been asked to assess the statewide potential for DSM and EE.  It has been some time since these subjects have been discussed in regulatory and public settings, especially as it pertains to the need for future electricity generation.  We have a long-standing relationship with utilities and appreciate their support and collaboration on many issues affecting energy utilization in our state.  The Public Staff of the N.C. Utilities Commission is an ally and recently recommended that we advise the N.C. Utilities Commission as to how we would manage a statewide Public Benefits Fund specifically for DSM and EE.  Other than the west coast, the northeast or selected mid-western states, the body of knowledge about DSM and EE has grown stale.  Furthermore, a lot has changed with respect to the way homes and business and industry use energy since DSM and EE were in vogue in the 80s and early 90s.  Many states and other jurisdictions lack the expertise and experience to evaluate and plan new programs.  We heard that NAESB has an excellent reputation in the development of standards and felt that this area might be an area that fit NAESB’s mission.  Please contact me with any questions regarding our attached request.  Sincerely,  Carl L. Wilkins, P.E., Director, Utility Services

REQUEST:

Efforts are underway throughout the electricity industry to develop and implement demand side management measures and techniques in order to moderate the growth for electricity.  However, a standardized method for quantifying the energy and demand impact of implementing proposed demand side management techniques does not exist.  Entities involved in these activities are using a wide variety of methods to estimate the benefits of these programs.  As various utilities across the nation look at implementing DSM and EE measures, it is evident that results may vary depending on many factors that are localized and at the discretion of the evaluating entity.  On the other hand there are fairly standardized techniques for evaluating and presenting the benefits and costs for a supply side option.   As regulatory commissions investigate utility integrated resource plans, the development and presentation of the DSM and EE options are vigorously challenged by interveners as being incomplete, inconsistent and not treated as fairly as supply side options.  Furthermore, utilities recognize the uncertainty of some proposed demand side options because they lack standardized quantitative justification which may address issues such as program persistence and other variables out of the DSM/EE program’s control. DSM and EE programs often fail to pass cost effectiveness tests (RIM, UTC, PCT, etc.) because the benefit/cost data that is presented may be inaccurate or based on poor assumptions.  Having a standardized method that is both recognized and understood by utilities, regulatory agencies, program administrators, consumer advocates and energy service professionals is vital. For example, the amount of energy reduction for a DSM measure in a small building can be simulated by a computer model, obtained by actual load research, using results from another similar program or estimated by engineering calculations. The benefits, costs and energy impacts from either of the aforementioned techniques can vary widely.

The proposed standard will be used by regulatory agencies, utilities, program administrators and any entity that are involved with quantifying impacts of a DSM or energy efficiency program.  This standard may become an important part of a utility’s integrated resource planning process.  As more electric utilities announce new base-load generation additions to their long-term resource plans, the opportunity for this proposed standard to be use becomes more evident.

Having a standardized process will prove beneficial to all stakeholders.  The amount of time and resources expended in today’s IRP hearings should be less if all parties adopt and use a standardized process and procedure for determining energy impacts of DSM and energy efficiency.  The number of interveners and the amount of interrogatories should diminish once an accepted standard is made known to all.  Future hearings should be less contentious, which will be appreciated by all parties.  This standard if developed and adopted will lower the regulatory cost of implementation.

RESOLUTION 11-15-06:  Combined with item 4 below.  Item 3 is underway now in PJM and is both a retail and wholesale electric issue.

5.	Participation

Submitted by Shay Reed, CostCo

Afternoon,

I recently attended the EEI conference national accounts meeting in Florida, and we were told that October 11th, 2006 is the deadline to be included for comments on several standards issues. After reading the memo I received, it appears that this is the comment deadline rather than inclusion in the comment group? Can you please confirm the requirements for inclusion in regards to NAESB standards? We would like to be involved, and hope we are not too late. Thank you for the information.

Shay Reed -

Thank you for your interest in NAESB standards development.   If you would like to submit comments, please send them to NAESB (naesb@naesb.org) by the end of this week.  Please let me know if you need any additional information.  Best regards,  Veronica Thomason

Submitted by:Denis George, Kroger

While I only saw this today and do not have time to submit substantive comments at this time, as a general matter The Kroger Co. - one of the largest grocery supermarket chains in the US (www.kroger.com) - would be happy to comment upon and participate in any initiative that would help bring uniform standards for retail EDI/XML transactions for both gas & electric utilities.  Please feel free to direct further correspondence on this matter to me directly.

RESOLUTION 11-15-06:  Combined with item 6 below.

6.	Electronic Billing

Submitted by Suzanne Figy, Director, Operations - Data Services,  Advantage IQ, Inc.

Hi Veronica, My name is Suzanne Figy and I am the Director of Operations - Data Services for Advantage IQ. Advantage IQ currently manages more than $9.3 billion in facility bills for more than 375 clients. We currently process and pay more than 500,000 bills/month supporting over 190,000 sites. Advantage IQ maintains a solid relationship with more than 16,000 utilities nationwide. Currently, we receive 21% of our incoming utility bills via EDI. We are of great interest in having NAESB develop some standards in the areas outlined in the annual plan. Given the volumes of electronic bills we are currently managing I would like to request that we be included in the planning discussions. I would like to ask that you add  myself as our representative.  We have a great amount of excitement around these initiatives and feel we can be a great asset to the discussions.  Please contact me if you need any additional information or have any further questions.  Thank you, Suzanne Figy

Ms. Figy,  Thank you for contacting our office with your request.  We will be happy to add your request to the list of NAESB Retail Annual Plan topics for discussion. Best regards,  Denise Rager

RESOLUTION 11-15-06:  Combined with item 5 above.  EDI transactions for electronic billing between utilities and national accounts customers is on the 2007 annual plan now and the business practices have already been developed.  XML transactions are not on the 2007 plan.  If Kroger and CostCo are interested in pursuing XML, we would need to identify both the sponsors/champions for this development and also the subject matter experts that would participate in XML development.  NAESB office will pursue determining if the interest level is high enough to warrant a conference call with applicable parties.

7.	Customer Interval Data

Under consideration by the Massachusetts EBT

Draft Letter Prepared on 9/12/06 RE:  Customer Interval Data

Dear Ms. Cottrell:

We, the undersigned competitive suppliers, third party providers and brokers, hereby request that the Department review a proposed change in the current practice regarding the authorization requirement for provision of customer interval metered usage data (“interval data”) to suppliers. The proposed change would simplify the practice, reduce costs, and allow for improved data security by making suppliers responsible for maintaining customer authorizations and thereby paving the way ultimately for interval data to be requested and provided using standard electronic business transactions.. The proposal has been discussed by the Massachusetts Electronic Business Transactions (“EBT”) Working Group, and the EBT has been authorized by the EBT electric distribution company members (EDCs) to represent their lack of objection to the change, provided it is acceptable to the Department.

Background: Increases in competitive market efficiency have revealed the existence of a bottleneck in the day-to-day operation of Massachusetts’ deregulated electricity supply marketplace in regards to the provision of interval data. The unnecessarily labor intensive nature of requesting and receiving interval data for both prospective and existing customers, acts as a hindrance to the ability of suppliers to offer accurately derived and timely priced innovative competitive supply products to commercial and industrial customers.  The process for provision of interval data to suppliers is governed by the EDCs’ interval data tariffs as approved by the MDTE.  Those tariffs provide that interval data will be made available to the customer or the customer’s “authorized agent.”  However, the tariffs do not specify how that authorization is to be demonstrated.  See, e.g.,  Massachusetts Electric Company, Optional Interval Data Service, M.D.T.E. No. 1034; Boston Edison Company, Optional Interval Data Service, M.D.T.E. No. 151.  The Department’s order approving those tariffs is similarly silent on the question of how the authorization is to be demonstrated.  Metering and Billing Services, D.T.E. 01-28 (Phase I) (May 18, 2001).

Current Practice: Regardless of the lack of an explicit written statement from the Department that delineates what constitutes authorization, it has been the interpretation of the supplier and EDC communities that the supplier would demonstrate authorization by providing a copy of a signed authorization to the EDC with any interval data request. This is the current procedure; an authorization form must be manually issued to the EDC and the EDC, in turn, must file and manage this paperwork in-house, prior to releasing customer data. This is the perceived requirement and current practice whether the customer is a prospect requesting pricing, or already a fully enrolled customer of the supplier submitting the request. Over time, this practice but has proven to be unnecessarily cumbersome for customers and suppliers, as well as for EDCs. For customers the most obvious impact is a delay in pricing from prospective suppliers in a market where even a day can make a material difference in pricing.

Proposed Practice:  We propose changing the current practice by removing the requirement that the customer authorization be provided to the utility.  Instead we suggest that suppliers be held responsible for obtaining, holding and maintaining the appropriate customer authorization for any requests they make. With such a change, the supplier would still obtain a written authorization from the customer, either in the form of a stand alone consent form or a supply contract with an authorization provision. Further, we would propose that suppliers be required to maintain a scanned version of the written authorization on file at the suppliers’ premises for the full length of the customer contract or 24 months, whichever is longer, and that such authorizations would be subject to audit by the Department. We also note that when the Supplier is requesting the interval data, it is assumed that they are paying the fee and will be billed accordingly from the utility. Under this proposal, the utility would then be released of the responsibility to obtain the authorization form and the cost of the request and would be liberated to honor the request for interval data without reference to paper files.  Suppliers have indicated a willingness to go one step further and incorporate an authorization provision into their customer contracts, should the Department accept this change in practice. In addition to saving time and manual effort, this step would pave the way for full EDI access to interval data in 2008, which is when the EDCs have indicated their systems would be ready to accept these requests electronically like other electronic business transactions sent via EDI. EDI works on a prescribed set of electronic communications between suppliers and distribution companies, and does not include a mechanism for the exchange of documents as part of that data transfer. The proposed change in procedure for authorizations would remove an important barrier to being able to request and receive interval data using the same standard vehicle used for all other utility/supplier data exchanges.   In the EDI scenario, the supplier would submit an interval data request to the utility via EDI using the customer’s account number as identifier and would represent that it has obtained the necessary customer authorization and is maintaining it on file. The utility would be free to rely on that representation, knowing that that supplier is subject to audit on any authorization by the DTE.  This is exactly how EDI transactions work in other contexts, for example, customer enrollments.  The supplier is required to obtain a written (or verified telephonic) authorization to enroll the customer, but is not required to file evidence of that authorization with the utility prior to enrollment acceptance, except upon request for audit.  Instead, the supplier simply submits an “enroll customer” request using the customer’s account number via EDI and the utility accepts that request as the supplier’s representation that it has obtained the necessary authorization.  The proposed change in practice for interval data requests would simply bring that practice in line with the procedure for customer enrollments and other supplier/utility transactions in Massachusetts, as well as with interval data practice in other regions of the country. The Massachusetts EBT members (both EDCs and suppliers) concur that this course of action is a win-win solution for everyone including the customer.  Provision of interval data would take place seamlessly without a need to wait for manual intervention and would mirror the same procedure we currently follow for all historic usage data requests.  We propose that this change in procedure apply to both historic interval data requests made for pricing prospective customers, as well as for monthly recurring interval reads used for forecasting and billing of a supplier’s actively enrolled customers. The former would allow prospective customer’s access to more timely pricing and product options in the marketplace, critical to making prudent business decisions in an ever-changing supply environment. The latter is necessary for timely billing of any non-fixed price product and is consistent with EPACT 2005's move toward providing customers with price sensitivity – more and more common in today’s market.

Benefits of the Change in Practice:  The Department has recognized, “historical interval load data are essential to the development of a strong competitive electric generation marketplace.” Metering and Billing Services, D.T.E. 01-28 (Phase I) at 14.  The availability of interval data improves the accuracy of forecasting and pricing.  It also enables the development of innovative products and services for customers, critical to maturation of the competitive marketplace.  The proposed change would greatly increase the efficiency of obtaining and receiving interval data and thus increase its availability for not only the EDC and suppliers, but more importantly, for customers. Therefore, we request that the Department review the proposed change in practice to allow suppliers to be the holder of record for customer interval data authorizations, whether they be within the customer’s supply contract or in a separate authorization form.

We respectfully request the Department’s expedited review of this proposed change in practice and thank you and the Department for your consideration.  Sincerely, Constellation NewEnergy, ConEdison Solutions, Direct Energy, Dominion Energy Services Group, Gestalt LLC, Hess, PPL Solutions, Select Energy, TransCanada

RESOLUTION 11-15-06:  The interval data is already in the model business practices for pre-enrollment activity.  The standards do not specifically require that the utility maintain the information.  For the EDI transactions, the 2007 plan already includes the development of EDI transactions.  If MA EBT is interested in pursuing standard EDI transactions through NAESB, we would ask that the leaders of the group participate in the NAESB TEIS and EDM subcommittees to further their expectations.   NAESB office will pursue determining if the interest level is high enough to warrant a conference call with applicable parties.

Projects that have been discussed but are not reflected on the 2007 plan nor have had requests prepared and submitted to NAESB are:

- Contracts:  development of additional retail contracts and addenda that support the base contract already under development

- Customer Choice Activities

- Distributed Generation

- Energy Renewal and Green Energy Programs

- Interruption and Curtailment Procedures

- Load Profiling – gas and electric requirements

- Review security standards as may be deemed necessary, such as Public Key Infrastructure (PKI).

- Low Income Strategies

- Model Business Practices between utilities and suppliers in day to day transactions with RTOs (joint initiative with the WEQ)

- Net Metering

- Renewables/Renewable Portfolio Standards – work with the wholesale quadrant on nationally traded renewable energy credit

- Distribution Company/Supplier communications of gas supply requirements

- Model Business Practices for communications between suppliers and customers

Reach out to SGA and AGA for subject matter experts.