[image: image2.png]0

I

0




North American Energy Standards Board

1301 Fannin, Suite 2350, Houston, Texas 77002

Phone:  (713) 356-0060, Fax:  (713) 356-0067, E-mail: naesb@naesb.org

Home Page: www.naesb.org

	NORTH AMERICAN ENERGY STANDARDS BOARD

Draft 2006 WEQ Annual Plan 
Adopted by the WEQ Executive Committee on November 29, 2005


	
	Item Description
	Completion

	Assignment


	1
	Develop business practices standards as needed to complement reliability standards

	
	Develop business practice standards to support and complement NERC reliability standards, NERC policies and NERC standards authorization requests (SARs).  Current NAESB activities underway to develop business practice standards that are supportive of this annual plan item are: 

	
	a)
	Make version 1 changes to business practices as requested.
	Ongoing
	BPS

	
	
	i)
	Make changes to business practices as related to inclusion of  functional model entities as NERC undertakes the same efforts
	As requested
	BPS

	
	
	ii)
	Review the NAESB WEQ “Version 0” business practice standards and remove any references to ERCOT (R05007)
	1st Q, 2006
	BPS

	
	
	
	
	

	
	
	

	
	b)
	Develop business practices to support Coordinate Interchange – update already adopted version 1 to reflect version 1 NERC CI (R03013, R05001, R05020)
	3rd Q, 2006
	BPS

	
	c)
	Develop business practice standards to support Operate Within Limits (R03017)
	2006
	BPS

	
	d)
	Develop business practices to support the reliability components of TLR

	
	
	i)
	Version 0 Split of TLR business practices from reliability components
	1st Q, 2006
	BPS

	
	
	
	

	
	
	ii)
	Continuous support of TLR Procedure in alignment with NERC efforts including version 1 development
	Ongoing
	BPS

	
	f)
	Determine any needed NAESB action in support of the Interchange Distribution Calculator (IDC).
	2006
	BPS

	
	g)
	Develop jointly with NERC a Joint NERC/NAESB Operating training manual.
	2006
	BPS

	2
	Develop business practice standards for Version 1 to support ATC calculations

	
	Develop version 1 business practice standards to better coordinate the use of the transmission system among neighboring transmission providers.  Such business practice standards would be based on recommendations from NERC's Long Term ATC/AFC Task Force and would involve revised procedures for the ATC calculation and/or revised protocols for coordination between neighboring transmission providers and/or amendments to existing TLR procedures.
	Pending
	BPS

	
	Note:  Awaiting revised clarified Request R05004 from NERC – to develop transmission service request and scheduling standards using TTC/ATC/AFC and CBM/TRM.

	3
	Develop business practices standards to improve the current operation of the wholesale electric market and develop and maintain business practice and communication standards for OASIS and Electronic Scheduling

	
	a)
	Develop and/or maintain business practice standards as needed for OASIS and electronic scheduling. Specific items to address include:

	
	
	
	
	
	

	
	
	
	

	
	
	i)
	Business Practices for the resale or reassignment of transmission service (R04006D)
	1st Q, 2006
	ESS/ITS

	
	
	
	

	
	
	ii)
	Implementation of "release" mechanism in the OASIS S&CP to complement non-firm redirects (R04006C1)
	1st Q, 2006
	ESS/ITS

	
	
	iii)
	Network Services:  determine if business practice standards or other support is needed to support use of OASIS for Network Service transactions (R04006E).
	3rd Q, 2006
	JISWG

	
	
	iv)
	Registry:  determine if business practice standards are needed to support the registry functions currently supported by NERC (R04037).
	2nd Q, 2006
	JISWG

	
	
	v)
	Adoption/maintenance of ESC use cases (R04007)
	1st Q, 2006
	ESS/ITS

	
	
	vi)
	Adoption/maintenance of Functional Requirements Document (R04007)
	1st Q, 2006
	ESS/ITS

	
	
	
	
	
	

	
	
	vii)
	e-Tag enhancements (including e-Tag specification changes) (R05018)
	2nd Q, 2006
	ESS/ITS

	
	
	viii)
	Document procedures used to implement the displacement/interruption terms of the Pro Forma tariff (R05019)
	3rd Q, 2006
	ESS/ITS

	
	
	ix)
	Incremental enhancements to OASIS as an outgrowth of the NAESB March 29, 2005 conference on the future of OASIS (R05026)
	TBD
	Not Assigned

	
	b)
	Develop and/or maintain standard communication protocols and cyber-security business practices as needed

	
	
	i)
	Develop companion business practices to NERC's Cyber Standard (CIP002-009), and specifically review section 1303-Personnel & Training to determine if business practices are needed.
	3rd Q, 2006
	ESS/ITS

	
	
	ii)
	Partner with the Department of Energy to perform a surety assessment on NAESB technical standards and respond to the surety assessment findings and recommendations.
	4th Q, 2006
	EC Officers

	
	
	iii)
	PKI Initiative (e-MARC) (R03007)
	1st Q, 2006
	JISWG

	
	c)
	Develop business practices as needed for clarification of definitions and terminology in the Standards of Conduct

	1st Q, 2006
	BPS

	
	d)
	Develop needed business practice standards for organization/company codes for NAESB standards – and address current issues on the use of DUNs numbers.
	4th Q, 2006
	Not Assigned

	
	
	Note:  Disposition of Item 3d depends on action by the Board of Directors on December 13, 2005.

	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	PROVISIONAL ITEMS

	1
	Develop business practice standards as requested by the regional and state advisory groups.

	2
	Using the NERC Interconnected Operations Services reference document (March 2002, version 1.1) as a guide and starting point, develop business practices as necessary for ancillary services and/or interconnected operating services transactions.

	3
	Develop and or modify business practices related to OATT reform resulting from the Notice of Inquiry, Docket No. RM05-25-000, FERC Notice Requesting Comments, “Preventing Undue Discrimination and Preference in Transmission Services”, issued September 16, 2005.

	4
	Evaluate the entries on the seams catalog, determine the need for business practice standards and draft the standards requests to develop business practice standards to complement or assist specific seams mitigation efforts as noted in the seams catalog.

	5
	Develop business practice standards according to approved and assigned standards requests that complement or assist specific seams mitigation efforts as noted in the seams catalog.

	6
	Develop business practice standards as related to the Effectiveness Study of Competitive Wholesale Markets (Congressional Mandate), Electric Energy Market Competition Task Force, Docket No. AD05-17-000, issued by the FERC on October 13, 2005.

	7
	Upon the issuance of the final order by FERC, develop and or modify business practices as requested by FERC related to OASIS or Version 0 business practices as filed by NAESB with the FERC on January 18, 2005, in Docket No. RM05-5-000.  The FERC Notice of Proposed Rulemaking, RM05-5-000, “Standards for Business Practices and Communication Protocols for Public Utilities,” was issued May 9, 2005.

	8
	Develop and/or maintain business practice standards to support gas-electric interdependencies

	
	Respond to requests as received that are related to Docket No. RM05-28-000.

	
	Respond directives related to the conclusions of the NAESB reports submitted in Docket No. RM05-28-000.

	
	Evaluate and develop business practice standards for Energy Day (R04016).

	
	Evaluate and develop business practice standards for electric scheduling timelines (R04020).



[image: image1]
NAESB WEQ EC and Subcommittee Leadership:

Executive Committee:  Lou Oberski (WEQ EC Chair) and Tony Reed (WEQ EC Vice Chair)

Standards Review Subcommittee:  Raj Rana, Narinder Saini, Ollie Frazier
Seams Subcommittee: Inactive

Business Practices Subcommittee & Task Forces: Kathy York & Joel Dison
Electronic Scheduling Subcommittee/Information Technology Subcommittee & Task Forces: Paul Sorenson, J.T. Wood and Sherri Monteith
· Coordinate Interchange:  Roman Carter

· OASIS: J.T. Wood and Wendy Weathers

Joint Interchange Scheduling Working Group (JISWG):  Bob Harshbarger

Glossary Subcommittee (to be renamed):  Sherri Monteith































Task Forces & Working Groups5





Development














Scoping





Joint Interchange Scheduling Working Group


(JISWG)





Information Technology Subcommittee (ITS)





Electronic Scheduling Subcommittee (ESS)





Business Practices Subcommittee (BPS)





Glossary Subcommittee (to be renamed)





Seams Subcommittee (inactive)





Standards Review Subcommittee (SRS)





Wholesale Electric Quadrant


Executive Committee (WEQ EC)








End Notes:





� Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed so as to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.


� The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the annual plan document.


� The changes to the Standards of Conduct requested by the Commission in NOPR Docket No. RM05-5-000 will be made as soon as possible.


� The Board of Directors determined to table items 4c and 4d at the June 22 ,2005 meeting.  Depending on the outcome of the board meeting on December 13, 2005, both Request Nos. R04016 and R04020 may be withdrawn by the submitters.


5 The WEQ EC and the subcommittees may create task forces, working groups and ad hoc groups to address specific topics within their scopes of effort.  





2006 NAESB Wholesale Electric Quadrant Annual Plan
Adopted by the WEQ Executive Committee on November 29, 2005
Page 1 of 5

