
ISO/RTO Work Plan for NAESB Wholesale EE/DSM Standards
	#
	Task
	Description
	Deliverable
	Completion Date
	Who

	1
	Finalize Framework
	The draft framework will serve as a basis for documenting the technical M&V requirements for the different ISO/RTO products. It should guide each ISO-RTO in answering the questions of Why, When, and What M&V is done.
	Each ISO should provide comments on the Objectives, Frequency and Description.  Each ISO/RTO should add any additional comments that it feels it needs to describe the products, (this will help to synthesize any commonalities between products and ISO/RTOs).   If the list of product classes are not representative, please comment.
	10/30/07

COMPLETE
	All

	2
	ISO/RTO Conference Call
	This call is designed to discuss comments submitted in regard to the Framework
	Come to consensus on the Framework
	Week of  November 19 , 2007  
COMPLETE

	All

	3
	Report to NAESB DSM/EE Standards Committee
	At the September 25th meeting the ISO/RTOs tacitly agreed to report back to the Committee on how we plan on completing the task by the end of the 1st quarter of 2008.
	Report to NAESB DSM-EE Task Force the status of the ISO/RTO Wholesale standards development.
	11/30/07

COMPLETE
	P. Wattles, E. Winkler

	4
	Add M&V technical data
	Each ISO/RTO will fill in the matrix with appropriate technical requirements and how the M&V activity is implemented (where appropriate) for each of its products and each M&V area.
	A Draft Matrix with the general description of the M&V areas, products and technical information in M&V requirements for each ISO/RTOs range of products.
	12/15/07

COMPLETE
	All

	5
	ISO/RTO Conference Call
	This call is designed to review  progress on data synthesis from the Framework
	Develop status update on development of wholesale standards 
	January 14, 2008. 

COMPLETE
	All

	6
	Report to NAESB DSM/EE Task Force
	Status report of Wholesale standards
	Report to NAESB the status of the ISO/RTO Wholesale standards development.
	1/23/2008

COMPLETE
	P. Wattles, E. Winkler

	7
	Update M&V Technical Data
	ISO/RTOs will update matrices with appropriate expanded technical requirements.
	Expanded draft Matrix
	1/30/2008

COMPLETE
	All

	8
	ISO/RTO Conference Call
	This call is designed to review  progress on data synthesis from the Framework
	Develop status update on development of wholesale standards 
	2/11/08  
COMPLETE
	All

	9
	Draft Wholesale Standards
	Synthesize Technical Requirements into draft Standards
	Draft Standards will be developed by processing the technical requirements provided by all the ISO/RTOs to find commonalities and or create ranges of requirements
	2/29/08

COMPLETE internal document
	E. Winkler lead, Scott COE, review by All

	10
	ISO/RTO Working Meeting
	This meeting is designed to review and discuss the draft wholesale standards.
	Provide agreement on draft  standards to be submitted to NAESB 
	3/11/08 -3/12/08
COMPLETE
	All

	11
	Revise Draft Outline of Standards
	Revised Draft Wholesale DR Standards outline based on working group session distributed to ISO/RTO working group
	Revised Draft Wholesale Standards Outline
	3/18/08

COMPLETE
	E. Winkler

	12
	Update M&V Technical Data
	Each ISO/RTO will revise entries in the matrix for appropriate technical requirements per the current draft matrix.  (IRC Demand Programs 2008-03-14.xls)
	A Draft Matrix with the general description of the M&V areas, products and technical information in M&V requirements for each ISO/RTOs range of products and services
	3/21/08
	All

	13
	Call to review Presentation & discuss presentation at DSM/EE Meeting
	Review of materials and scope of presentation at NAESB DSM/EE standards development meeting, Houston, TX March 28, 2008
	Presentation materials for meeting
	3/26/08
	P. Wattles, E. Winkler

	14
	NAESB DSM/EE Standards Committee
	ISO-RTO documents presented as a draft for wider NAESB stakeholder consideration and comment
	Report to NAESB on documented ISO/RTO Wholesale DR M&V standards for use in developing proposed NAESB standards and/or model business practices.
	3/28/08

Houston TX
	P. Wattles, E. Winkler, S. Coe

	15


	ISO/RTO Working Meeting
	This meeting is designed to review and discuss the draft wholesale standards.
	Provide agreement on draft  standards to be submitted to NAESB 
	Mid May, 2008, TBD
	All

	16
	NAESB DSM/EE Standards Committee
	ISO-RTO documents presented as a draft for wider NAESB stakeholder consideration and comment
	Report to NAESB on documented ISO/RTO Wholesale DR M&V standards for use in developing proposed NAESB standards and/or model business practices.
	5/30/08

Holyoke, MA
	P. Wattles, E. Winkler,

S. Coe

	17
	NAESB DSM/EE Standards Committee
	ISO-RTO documents presented as a draft for wider NAESB stakeholder consideration and comment
	Report to NAESB on documented ISO/RTO Wholesale DR M&V standards for use in developing proposed NAESB standards and/or model business practices.
	7/30/08
TBD
	P. Wattles, E. Winkler,

S. Coe

	18

	ISO/RTO Working Meeting
	This meeting is designed to review and discuss the draft wholesale standards.
	Provide agreement on draft  standards to be submitted to NAESB 
	Mid Sept, 2008, TBD
	All

	19
	Draft Wholesale DR Standards
	Final Draft Wholesale Standards Completed for submittal to NAESB
	Completed draft ISO/RTO contribution of wholesale DR M&V standards
	9/30/08
	E. Winkler,
S. Coe

	20
	NAESB DSM/EE Standards Committee
	ISO-RTO documents presented as a draft for wider NAESB stakeholder consideration and comment
	Report to NAESB on documented ISO/RTO Wholesale DR M&V standards for use in developing proposed NAESB standards and/or model business practices.
	9/30/08
Austin, TX
	P. Wattles, E. Winkler,

S. Coe


Denotes added items 1/14/08

Denotes added items 3/14/08 
Contact List:

	First
	Last
	CO.
	Phone
	Email

	Bill
	Wilbur
	IESO
	 
	bill.wilbur@ieso.ca

	Chuck
	Goldman
	LBL
	510-486-4637
	CAGoldman@lbl.gov

	Chris
	Brown
	NYISO
	518-356-7546
	cbrown@nyiso.com

	Dave
	LaPlante
	ISO NE
	413-535-4120
	dlaplante@iso-ne.com

	Donna
	Pratt
	NYISO
	518-356-8758
	dpratt@nyiso.com

	Eric
	Winkler
	ISO NE
	413-540-4513
	ewinkler@iso-ne.com

	George
	Porter
	NBSO
	 
	george.porter@nbso.ca

	Gordon
	Nadeau
	AESO
	403-539-2568
	Gordon.Nadeau@aeso.ca

	Gerrud
	Wallaert
	SPP
	501-614-3358
	gwallaert@spp.org

	Henry
	Yoshimura
	ISO NE
	413-540-4460
	hyoshimura@iso-ne.com

	Jeanette
	Briggs
	IESO
	 
	jeannette.briggs@ieso.ca

	John
	Goodin
	CAISO
	916-608-7154
	JGoodin@caiso.com

	John
	Norden
	ISO NE
	 
	jnorden@iso-ne.com

	John
	Antonakos
	IESO
	905-403-6979
	john.antonakos@ieso.ca

	Bob
	Jones
	PJM
	 
	jonesr@pjmexch01.pjm.com

	Kevin
	Melanson
	NBSO
	 
	kevin.melanson@nbso.com

	Pete
	Langbein
	PJM
	610-666-4583
	langbp@pjm.com

	Mike
	Robinson
	MISO
	317-249-5741
	mrobinson@midwestiso.org

	Paul
	Wattles
	ERCOT
	512-248-6578
	pwattles@ercot.com

	Robert
	Burke
	ISO NE
	413-535-4356
	rburke@iso-ne.com

	Bob
	Laurita
	ISO NE
	413-540-4398
	rlaurita@iso-ne.com

	Rob
	Baker
	AESO
	 
	rob.baker@aeso.ca

	Scott
	Coe
	Consultant
	413- 540-4594
	scoe@iso-ne.com

	Steve
	Krein
	ERCOT
	512-248-6830
	skrein@ercot.com

	Chris
	Caulfield
	NYISO
	 
	

	 Li
	Zhang 
	MISO 
	317-249-5352 
	lzhang@midwestiso.org 


Please add names to this list if appropriate




























































NAESB EE/DSM Wholesale Standards
March 21, 2008
ISO/RTO Working Group

Page 1 of 3

