| NORTH AMERICAN ENERGY STANDARDS BOARD 2008 ANNUAL PLAN for the RETAIL GAS and ELECTRIC QUADRANTS Adopted by the NAESB Board of Directors on December 18, 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Item Number & Description |  |  |  |  | Completion | Assignment |
| 1 |  | Electronic Retail Billing. |  |  |  |  |  |  |
|  |  |  | Develop Technical Electronic Implementation Standards – Electronic Retail Billing Status: Underway |  |  |  | 1st Q, 2009 | TEIS |
| 2 | Customer Enrollment, Drop and Account Information Change including Using a Registration Agent |  |  |  |  |  |  |  |
|  | a. |  | Develop information requirements for submitting and receiving, processing and fulfilling a customer’s request to enroll with or leave a supplier (including suppliers dropping customers) and for maintaining current customer account information, and for notifying affected parties. Status: Completed |  |  |  | 3rd Q, 2008 | IR |
|  | b. |  | Develop Technical Electronic Implementation Standards – Customer Enrollment, Drop and Account Information Change, Status: Completed |  |  |  | 3rd Q, 2008 | TEIS |
| 3 | Customer Enrollment, Drop and Account Information Change Using a Registration Agent |  |  |  |  |  |  |  |
|  |  |  | Develop practices when using a Registration Agent for submitting and receiving, processing and fulfilling a Customer’s request to enroll with or leave a Supplier (including Suppliers dropping Customers) and for maintaining current Customer account information, and for notifying affected parties. |  |  |  |  |  |
|  |  |  | i) |  |  | Customer Enrollment Status: Completed | 4th Q, 2007 | Texas Task Force/ BPS |
|  |  |  | ii) |  |  | Customer Drop Status: Completed | 1st Q, 2008 | Texas Task Force/ BPS |
|  |  |  | iii) |  |  | Account Information Change Status: Completed | 1st Q, 2008 | Texas Task Force/ BPS |
|  |  |  | iv) |  |  | ESI ID Setup Status: Completed | 4th Q, 2008 | Texas Task Force/ BPS |
|  |  |  | v) |  |  | ESI ID Change Status: Completed | 4th Q, 2008 | Texas Task Force/ BPS |
| 4 | Review and Discuss application of any other existing model business practices for the Registration Agent model Status: Completed |  |  |  |  |  | 3rd Q, 2008 | BPS |
| 5 | Customer Inquiries |  |  |  |  |  |  |  |
|  | a. |  | Develop procedures for responding to customer inquiries directed to Distributors and/or Suppliers and for notification of the other party. Status: Underway |  |  |  | 1st Q, 2009 | Texas Task Force/BPS |
| 6 | Develop NAESB Certification checklist criteria for Retail Quadrants to be used in the NAESB Certification Program. Status: Not Started. Dependent upon publication of Version 1.1 at a minimum, but more dependent upon completion of Customer Choice efforts. |  |  |  |  |  | 2009 | TEIS |
| 7 | Address issues raised in the Department of Energy’s Sandia National Laboratories on NAESB technical standards and respond to the surety assessment findings and recommendations. Status: Completed |  |  |  |  |  | 1st Q, 2008 | TEIS |
| 8 | Review and develop needed model business practices for a standardized method for quantifying benefits, savings, cost avoidance and/or the reduction in energy demand and usage derived from the implementation of demand side management and energy efficiency programs. This effort will include demand side response, energy efficiency programs and metering, including the 'curtailment service provider' program. Status: Underway |  |  |  |  |  | 2008 | Joint WEQ/Retail DSM Subcommittee |
|  | a. |  |  | Develop matrix and business practice standards for measurement and verification for demand response programs in ISO/RTO footprint areas. Status: Underway |  |  | 4th Q, 2008 | Joint WEQ/Retail DSM Subcommittee |
|  | b. |  |  | Develop matrix and business practice standards for measurement and verification for demand response programs in non-ISO/RTO footprint areas. Status: Underway |  |  | TBD | Joint WEQ/Retail DSM Subcommittee |
|  | c. |  |  | Develop preamble for business practice standards for measurement and verification for demand response and energy efficiency programs. Status: Underway |  |  | 1st Q, 2009 | Joint WEQ/Retail DSM Subcommittee |
|  | d. |  |  | Develop glossary for business practice standards Status: Underway |  |  | 1st Q, 2009 | Joint WEQ/Retail DSM Subcommittee |
|  | e. |  |  | Support retail development of matrix and model business practice standards for measurement and verification for demand response programs Status: Underway |  |  | 1st Q, 2009 | Joint WEQ/Retail DSM Subcommittee |
|  | f. |  |  | Develop business practice standards to measure and verify energy reductions that are made to comply with a Renewable Portfolio Standard that included energy efficiency or a stand-alone Energy Efficiency Portfolio Standard. Status: Not Started |  |  | Phase 2 | Joint WEQ/Retail DSM Subcommittee |
|  | g. |  |  | Develop business practice standards to factor Demand Control and Energy Efficiency programs into reliability / supply decisions at the wholesale level for generation and transmission planning and operations. Status: Not Started. |  |  | Phase 2 | Joint WEQ/Retail DSM Subcommittee |
|  | h. |  |  | Develop business practice standards to support cap and trade programs for green house gas. Status: Not Started. |  |  | Phase 2 | Joint WEQ/Retail DSM Subcommittee |
| 9. | Revise the Trading Partner Agreement TPA by removing the Exhibits from the agreement and relegate such information as contained in the Exhibits to operational worksheet(s), (R08015). Status: Underway |  |  |  |  |  | 1st Q, 2009 | Joint Retail/WGQ Contracts |
| Program of Standards Maintenance & Fully Staffed Standards Work |  |  |  |  |  |  |  |  |
|  |  | Business Practice Requests |  |  |  |  | Ongoing | Assigned by the EC |
|  |  | Information Requirements and Technical Mapping of Business Practices |  |  |  |  | Ongoing | Assigned by the EC |
|  |  | Ongoing Interpretations for Clarifying Language Ambiguities |  |  |  |  | Ongoing | Assigned by the EC |
|  |  | Ongoing Maintenance of Code Values and Other Technical Matters |  |  |  |  | Ongoing | Assigned by the EC |
|  |  | Ongoing Development and Maintenance of Definitions |  |  |  |  | Ongoing | Glossary |
| Provisional Activities |  |  |  |  |  |  |  |  |
|  |  | Joint Effort: |  |  |  |  |  |  |
|  |  |  |  |  | Supplier Certification: Develop practices for Distribution Companies to register/certify new Suppliers when they seek to begin doing business in the Distribution Company’s service area. |  |  |  |
|  |  |  |  |  | Modify TPA as necessary. |  |  |  |
|  |  |  |  |  | Review security standards as may be deemed necessary, such as Public Key Infrastructure (PKI). |  |  |  |
|  |  |  |  |  | Review existing body of model business practices for consistency and develop or modify model business practices as needed. |  |  |  |
|  |  | Retail Electric Quadrant Effort Only: |  |  |  |  |  |  |
|  |  |  |  |  | Retail Meter Data Validation, Editing & Estimating: Develop procedures for insuring the integrity and validity of retail customer metering data that is needed by utilities and suppliers for billing, etc. Issues related to unbundled or competitive metering are not to be considered. |  |  |  |
|  |  |  |  |  | Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market. Note: will need to be coordinated with the WEQ for the REQ. |  |  |  |
|  |  | Retail Gas Quadrant Effort Only: |  |  |  |  |  |  |
|  |  |  |  |  | Examine Wholesale Gas Quadrant Non-EDM Standards for applicability to retail business practices. |  |  |  |
|  |  |  |  |  | Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market. |  |  |  |

Retail Electric & Retail Gas

Quadrant Executive Committees

(REQ and RGQ ECs)

Business Practices Subcommittee (BPS)

Contracts Subcommittee (dormant)

Glossary Subcommittee

Information Requirements Subcommittee (IR)

Technical Electronic

Implementation Subcommittee (TEIS)

Model Business

Practice

Development

Task Forces & Working Groups

Technical

Standards

Development

Joint Retail/WEQ DSM-EE Subcommittee

NAESB Retail Subcommittee Leadership:

Executive Committee:  Mike Novak, Chair (RGQ), Ruth Kiselewich, Chair (REQ)

Business Practices Subcommittee:  Phil Precht (RGQ), Mary Edwards and Dan Jones (REQ)

Information Requirements Subcommittee: Jennifer Teel (REQ)

Technical Electronic Implementation Subcommittee: Dan Rothfuss (RGQ)

Glossary Subcommittee:  Don Sytsma (RGQ), Mary Edwards and Patrick Eynon (REQ)

DSM-EE Subcommittee: Ruth Kiselewich, David Koogler (REQ), Roy True (WEQ), Paul Wattles (WEQ)

End Notes Retail Plan:

As outlined in the NAESB Bylaws, the REQ and RGQ will also address requests submitted by members and assigned to the REQ and RGQ through the Triage Process.

Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.

The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the annual plan document.

This work is considered routine maintenance and thus the items are not separately numbered. The REQ and RGQ ECs will assign maintenance efforts on a request-by-request basis.

The ECs and the subcommittees can create task forces and working groups to support their development activities for development of model business practices and technical standards.