| NORTH AMERICAN ENERGY STANDARDS BOARD 2008 WEQ Annual Plan Approved by the Board of Directors on December 18, 2008 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Item Description |  |  |  |  | Completion | Assignment |
| 1 | Develop business practices standards as needed to complement reliability standards |  |  |  |  |  |  |
|  | Develop business practice standards to support and complement NERC reliability standards, NERC policies and NERC standards authorization requests (SARs) using the NERC/NAESB Coordination Joint Standards Development Process as appropriate. Current NAESB activities underway to develop business practice standards that are supportive of this annual plan item are: |  |  |  |  |  |  |
|  | a) | Make version 2 changes to business practices as requested. |  |  |  |  |  |
|  |  | i) |  | Make changes to business practices as related to inclusion of the NERC Reliability Functional Model functional model entities as NERC undertakes the same efforts. Status: No requests |  | As requested | BPS |
|  |  | ii) |  | Continuous support of TLR Procedure in alignment with NERC efforts on TLR Phase II and Phase III which would be included in version 2 development. Status: Complete The “Continuous Support of TLR Procedure in Alignment with NERC Efforts on Phase II and Phase III” recommendation was approved by the BPS to post for the formal comment period. For 2009 specific items for TLR coordination with NERC will be added as needed. |  | 3rd Q, 2008 | BPS |
|  | b) | Develop business practices to support Coordinate Interchange – R05020 “Include a guideline for rounding schedules with partial mWh's in the coordinate interchange business practice WEQ BPS-002-000” Status: Underway |  |  |  | 3rd Q, 2009 | JISWG |
|  | c) | Operate Within Limits (R03017) as coordinated with the NERC schedule on the same development for reliability standards |  |  |  |  |  |
|  |  | i) |  | Review the need to develop business practice standards to support Operate Within Limits (R03017) Status: Completed |  | 1st Q, 2008 | SRS |
|  |  | ii) |  | Develop business practice standards to support Operate Within Limits (R03017) Status: Completed No standards are needed at this time |  | 2nd Q, 2008 | BPS |
|  | d) | Prepare recommendations for future path for TLR in concert with NERC, which may include alternative congestion management procedures Status: Underway |  |  |  | 2009 | BPS |
|  | e) | Conduct analysis as to whether standards can be developed which outline a standardized process for the coordination and execution of emergency energy schedules. These would be complementary standards to EOP-002-2 Requirements R4 and R6 (SRS Analysis of EOP-002-2 R4 & R6) Status: Not Started |  |  |  | 1st Q, 2009 | JISWG |
|  | f) | Review Market System Back-Up existing language and review of existing back-up language Status: Completed Per the guidance from the WEQ Executive Committee after presenting the Request for Executive Committee Guidance on WEQ 2008 Provisional Item 5 the SRS developed and approved a “no action” recommendation to close out this annual plan item |  |  |  | 4th Q, 2008 | SRS |
|  | g) | Provide complementary business practice standards to support Coordinate Operations Standards Authorization Request assigned to NERC (R03014) Status: Completed Based on the SRS review of related documents and EC updates to the WEQ Annual Plan in May 2004 where R03014 was noted as completed the SRS approved a “no action” recommendation to close out this standards request. |  |  |  | 3rd Q, 2008 | SRS |
| 2 | Develop business practice standards in support of the FERC RM05-25-000 and RM05-17-000 (OATT Reform) |  |  |  |  |  |  |
|  | a) | Develop version 2 business practice standards to better coordinate the use of the transmission system among neighboring transmission providers. Such business practice standards would be based on recommendations from NERC's Long Term ATC/AFC Task Force and would involve revised procedures for the ATC calculation and/or revised protocols as determined by the final order. Status: Underway Development is using joint standards development process with NERC. Request R050004 was expanded to include the Order No. 890 (Docket Nos. RM05-25-000 and RM05-17-000) and Order No. 890-A (Docket Nos. RM05-17-001, 002 and RM05-25-001, 002), “Preventing Undue Discrimination and Preference in Transmission Services”, issued April 11, 2007). |  |  |  |  |  |
|  |  | i) |  | Group 1: Conditional Firm, Annotations For ATC; Load Forecast And Actual Load; Re-Bid Of Partial Service; And Preconfirmation Priority |  |  |  |
|  |  |  |  | - Conditional Firm, Annotations For ATC; Load Forecast And Actual Load; Re-Bid Of Partial Service; And Preconfirmation Priority S&CP Requirements Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 4th Q, 2007 | ESS/ITS |
|  |  |  |  | - Conditional Firm Business Practice Standards associated with S&CP Requirements completed in 2(a)(i)(1) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 3rd Q, 2008 | ESS/ITS |
|  |  |  |  | - Annotations For ATC Business Practice Standards associated with S&CP Requirements completed in 2(a)(i)(1) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | BPS, ESS/ITS |
|  |  |  |  | - Load Forecast And Actual Load Business Practice Standards associated with S&CP Requirements completed in 2(a)(i)(1) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | BPS, ESS/ITS |
|  |  |  |  | - Re-Bid Of Partial Service Business Practice Standards on a Single Transmission Provider’s System associated with S&CP Requirements completed in 2(a)(i)(1) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | ESS/ITS |
|  |  |  |  | - Preconfirmation Priority Business Practice Standards associated with S&CP Requirements completed in 2(a)(i)(1) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | ESS/ITS |
|  |  |  |  | - OASIS Exemptions Appendix Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 4th Q, 2007 | ESS/ITS |
|  |  | ii) |  | Group 2: Metrics; Redispatch Cost Posting |  |  |  |
|  |  |  |  | - Metrics Related to Provision of Transmission Service (Paragraph 413 of Order 890) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | ESS/ITS |
|  |  |  |  | - Metrics Related to Performance of Transmission Studies (Paragraphs 1308 through 1317 of Order 890 Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | ESS/ITS |
|  |  |  |  | - Redispatch Cost Posting - Monthly average cost of redispatch - A high and low redispatch for the month Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | ESS/ITS |
|  |  | iii) |  | Group 3: Network Service On OASIS |  |  |  |
|  |  |  |  | - Use of OASIS to Make Electronic Requests to Designate and Terminate Network Resource Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Ability to Query Requests to Designate and Terminate Network Resources and Allow for Queries of All Information Provided with Designation Requests Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Masking of Designated Network Resource Operating Restrictions and Generating Cost Information Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Procedural Requirements for Submitting Designations over new OASIS Functionality Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Specify How Designated Network Service Informational Postings are Posted on OASIS Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Set Forth the Treatment of OASIS Requests when the Customer Fails to Provide the Necessary Attestation Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Procedural Requirements for Submitting Both Temporary and Indefinite Terminations of Network Resources Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Procedures for Submitting and Processing Requests for Concomitant Evaluations of Transmission Requests and Temporary Terminations Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  | iv) |  | Group 4: Pre-Emption; Request No. R05019; and Revisions to Standard 9.7 |  |  |  |
|  |  |  |  | - Pre-Emption Status: Not Started |  | 2nd Q, 2009 | ESS/ITS |
|  |  |  |  | - Request No. R05019 Status: Not Started |  | 2nd Q, 2009 | ESS/ITS |
|  |  |  |  | - Revisions to Standard 9.7 Status: Underway This item also addresses work in 2006 WEQ AP 3a(x). |  | 2009 | EC Task Force |
|  |  |  |  | - Posting of Existing Transmission Commitments (ETC) (moved from Group 1) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 2nd Q, 2008 | BPS, ESS/ITS |
|  |  | v) |  | Group 5: Paragraph 1377 |  |  |  |
|  |  |  |  | - Paragraph 1377 Status: Not Started |  | 2nd Q, 2009 | ESS/ITS |
|  |  |  |  | - Re-Bid Of Partial Service across Multiple Transmission Providers’ Systems Status: Not Started |  | 2nd Q, 2009 | ESS/ITS |
|  |  | vi) |  | Group 6: Miscellaneous (Paragraphs 1390 and 1627 of Order 890) |  |  |  |
|  |  |  |  | - Paragraph 1390 of Order 890 Status: Not Started |  | 2nd Q, 2009 | ESS/ITS |
|  |  |  |  | - Paragraphs 1627 of Order 890 Status: Not Started |  | 2nd Q, 2009 | ESS/ITS |
|  |  |  |  | - Redispatch Cost Posting to allow for posting of third party offers of planning redispatch services. Status: Not Started |  | 2nd Q, 2009 | ESS/ITS |
|  |  |  |  | - Posting of Existing Transmission Commitments (ETC) (moved from Group 1) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 2nd Q, 2008 | ESS/ITS |
|  |  | vii) |  | Group 7: Tagging for Conditional Firm Service |  |  |  |
|  |  |  |  | - Tagging for Conditional Firm Service Status: Completed Published Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 2nd Q, 2008 | ESS/ITS |
|  | b) | Develop the needed business practices as companion to the NERC standards for ATC related efforts. |  |  |  |  |  |
|  |  | i) |  | Develop standards to support existing Request No. R05004. |  |  |  |
|  |  |  |  | 1. The processing of transmission service requests, which use TTC/ATC/AFC, in coordination with NERC changes to MOD 001 where the allocation of flowgate capability based on historical Network Native Load impacts the evaluation of transmission service requests, requiring the posting of those allocation values in conjunction with queries of service offerings on OASIS Status: Underway |  | 1St Q, 2009 | ESS/ITS |
|  |  |  |  | - Remaining requirements documented in R05004 and R05004A. Status: Completed |  | 3rd Q, 2008 | BPS, ESS/ITS |
|  |  | ii) |  | Develop Business Practice Standards for Existing Transmission Commitments (ETC) |  |  |  |
|  |  |  |  | - Develop the Business Practice Standards complementary to NERC Reliability Standards for Existing Transmission Commitments (ETC) to create a “consistent approach for determining the amount of transfer capability a transmission provider may set aside for its native load and other committed uses”, including the elements of ETC for full implementation of the NERC MOD-001 reliability standard. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 2nd Q, 2008 | BPS, ESS/ITS |
|  |  |  |  | - Business practice standards for accounting for counterflows. These standards will be included in the ATC business practice standards. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | June 1, 2008 | BPS ESS/ITS |
|  |  | iii) |  | Capacity Benefit Margin (CBM) Business Practices |  |  |  |
|  |  |  |  | - Determine if business practice standards are needed, and if so, develop them to set forth “how the CBM value shall be determined, allocated across transmission paths, and used” and how transmission providers will “reflect the set-aside of transfer capability as CBM in the development of the rate for point-to-point transmission service.” The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed The NAESB subcommittees have determined the CBM requirements have been documented in the NERC MOD-004 to address this item, so no further action is required by NAESB. Please note that when the related NERC reliability standards are adopted, the subcommittee leadership will review to determine if additional action by NAESB is needed. |  | 3rd Q, 2008 | BPS, ESS/ITS |
|  |  |  |  | - Business practice standards that include an OASIS mechanism to “allow for auditing of CBM usage.” The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed |  | 3rd Q, 2008 | BPS, ESS/ITS |
|  |  |  |  | - Any additional business practice standards needed to complement the NERC CBM reliability standards (MOD004) created as a result of this effort. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed |  | 3rd Q, 2008 | BPS, ESS/ITS |
|  |  | iv) |  | Transmission Reliability Margin Business Practices: |  |  |  |
|  |  |  |  | - Transmission Reliability Margin (TRM): Business Practice Standards to complement the NERC reliability standards for TRM. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed The NAESB subcommittees have determined TRM requirements have been documented in previously submitted recommendations, so no further action is required by NAESB. |  | April 8, 2008 | BPS, ESS/ITS |
|  |  |  |  | - The business practice standards will include specification of the appropriate uses of TRM and when transmission providers may set aside TRM. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development Status: Completed The NAESB subcommittees have determined TRM requirements have been documented in previously submitted recommendations, so no further action is required by NAESB. |  | April 8, 2008 | BPS, ESS/ITS |
|  |  |  |  | - Any additional business practice standards needed to complement the NERC TRM reliability standards (MOD008) created as a result of this effort. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed The NAESB subcommittees have determined TRM requirements have been documented in previously submitted recommendations, so no further action is required by NAESB. |  | April 8, 2008 | BPS, ESS/ITS |
|  |  | v) |  | Business Practice Standards for ATC and AFC Calculation Methodologies to complement the NERC reliability standards created for ATC and AFC Methodologies (NERC MOD001 (Available Transfer Capability); NERC MOD028 (Network Response Available Transfer Capability); NERC MOD029 (Rated System Path Available Transfer Capability); and NERC MOD030 (Flowgate Network Response Available Transfer Capability)): |  |  |  |
|  |  |  |  | - Business practice standards to address the frequency and posting requirements for all ATC components that are complementary to the related NERC reliability standards. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed The subcommittee determined no additional standards are required from what is already documented in the “ATC Information Link (2008 Annual Plan 2.b.vii)” recommendation and what is required for ATC postings under the previously ratified recommendation “Modifications to WEQ-001 to comply with modifications to 18 C.F.R. 37.6 and 37.7 within Order 890 with Minor Corrections applied on February 27, 2008.” |  | April 23, 2008 | BPS/ESS/ITS |
|  |  |  |  | - Business practice standards for data exchange for ATC modeling complementary to the related NERC reliability standards including any OASIS posting requirements to achieve the data exchange. The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development. Status: Completed The NAESB subcommittees have determined the data exchange requirements have already been documented in the NERC standards, so no further action is required by NAESB. |  | 1st Q, 2008 | BPS/ESS/ITS |
|  |  |  |  | - Business practice standards that will set forth how transmission providers will post “explanations of the reason for a change in monthly and yearly ATC values on a constrained path.” The standards will include a requirement that that the transmission provider posts the reason for the change in a narrative form. The posted information will include “the (1) specific events which gave rise to the change and (2) new values for ATC on that path (as opposed to all points on the network).” The business practices developed to address this item will not require to coordination with the NERC Order 890 reliability standards development. Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | BPS/ESS/ITS |
|  |  |  |  | - Business practice standards for posting on OASIS of the “underlying load forecast assumptions for all ATC calculations”. The business practices developed to address this item will not require to coordination with the NERC Order 890 reliability standards development Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | BPS/ESS/ITS |
|  |  |  |  | - Business practice standards for posting on OASIS of the “actual daily peak load for the prior day.” The business practices developed to address this item will not require to coordination with the NERC Order 890 reliability standards development Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | BPS/ESS/ITS |
|  |  | vi) |  | Business practice standards to complement NERC reliability standards for Transfer Capability in response to new NERC Supplemental SAR: Revisions to Existing Standards MOD001-MOD009, FAC12-13 This item was added as a result of the Supplemental SAR NERC created in case additional business practices are needed as a result of the work on this SAR by NERC. It does not have a cite in Order 890. This item will require coordination with the NERC Order 890 reliability standards development. Status: Completed |  | May 1, 2008 | BPS, ESS/ITS |
|  |  | vii) |  | Business practice standards to set forth the procedure for input on TTC and ATC methodologies and values. (During the Order 890 NERC and NAESB joint standards development effort, it was determined that the standards contained in MOD003 should be business practice standards instead of reliability standards. NERC has requested that NAESB adopt the standards as business practices via correspondence to Ms. McQuade, NAESB President.) This item will require coordination with the NERC Order 890 reliability standards development because the language to address this item is contained within a draft standards that addresses items that are dependent on NERC deliverables, i.e., the requirements to create an “ATC Information Link” on OASIS. There is no Order 890 cite for this item. Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  | 1st Q, 2008 | BPS, ESS/ITS |
|  | c) | Develop version 1 business practice standards to support transparency reporting and related functions that may be required as a result of the final order. Status: Completed The Executive Committee did not approve the recommendation submitted by the EC Task Force. Instead, they approved a “No Action” Recommendation for this annual plan item at their October 6, 2008 meeting |  |  |  | 3rd Q 2008 | EC Task Force |
| 3 | Develop business practices standards to improve the current operation of the wholesale electric market and develop and maintain business practice and communication standards for OASIS and Electronic Scheduling |  |  |  |  |  |  |
|  | a) | Develop and/or maintain business practice standards as needed for OASIS and electronic scheduling. Specific items to address include: |  |  |  |  |  |
|  |  | i) |  | Develop OASIS S&CP changes to support OASIS business practices. Status: Completed Dependent on development of OASIS business practices |  | 3rd Q 2008 | ESS/ITS |
|  |  | ii) |  | Network Services: Determine and develop needed business practice standards or other support is needed to support use of OASIS for Network Service transactions (R04006E). (Related to AP 2(a)(iii)) Status: Underway |  | 1st Q, 2009 | ESS/ITS |
|  |  | iii) |  | Registry (TSIN): Determine and develop needed business practice standards to support the registry functions currently supported by NERC (R04037, R06027). Status: Underway |  |  |  |
|  |  |  |  | 1) | Work with the NAESB counsel to develop a confidentiality agreement, (R07013) | 2009 | BPS |
|  |  |  |  | 2) | Transition the TSIN Registry from NERC to NAESB. | 2009 | NAESB Staff |
|  |  |  |  | 3) | Review and correct the Coordinate interchange Business Practice Standard as noted during the development of the e-Tag 1.8 development process. | 3rd Q, 2009 | JISWG |
|  |  | v) |  | Document procedures used to implement the displacement/interruption terms of the Pro Forma tariff (R05019). Status: Not Started |  | 3rd Q, 2009 | ESS/ITS |
|  |  | vi) |  | Make incremental enhancements to OASIS as an outgrowth of the NAESB March 29, 2005 conference on the future of OASIS (R05026). Scoping statement completed by SRS and assignments made to BPS, ESS/ITS and JISWG. |  |  |  |
|  |  |  |  | 1) | Represent ALL pre-Order 888 (“grandfathered”) transmission and ancillary services in current use in OASIS Status: Completed | 3rd Q, 2008 | BPS, ESS/ITS |
|  |  |  |  | 2) | Eliminate Masking of TSR tag source and sink when requested status is denied, withdrawn refused, displaced, invalid, declined, annulled or retracted Status: Not Started | 3rd Q, 2009 | ESS/ITS |
|  |  |  |  | 3) | Initiate standard that requires ALL historical transmission service reservations to be available for review up to a number of years in the past. Status: Completed | 3rd Q, 2008 | ESS/ITS |
|  |  |  |  | 4) | Initiate standard that eliminates the disparity of posting “sensitive” information. This standard should also include procedures of user certification that allows access to this class of information. Status: Not Started | 2009 | ESS/ITS |
|  |  |  |  | 5) | Enhance the TSR result postings to allow showing of (i) limiting transmission elements and (ii) available generation dispatch options that would allow acceptance of reservation request. Status: Not Started | 2009 | ESS/ITS |
|  |  |  |  | 6) | Standardize the availability of TSR study result postings, eliminating practice of some Transmission Owners that charge for viewing these documents. Status: Completed This item was completed with Recommendation (2008 AP Item 2.a.i.5, 2008 AP Item 2.a.i.6, and 2008 AP Items 2.a.ii.1-3) WEQ-001 Changes for Rebid of Partial Service, Preconfirmation Priority, and Group 2: Metrics; Redispatch Cost Posting. | 1st Q, 2008 | ESS/ITS |
|  |  | vii) |  | Respond to issues in FERC Order No. 676 (Docket No. RM05-5-000) – NAESB WEQ Standards 001 9.7, (paragraph 51 of the order). Status: Underway Item was assigned to group 4, reference 2007 WEQ AP item 2(a)(iv)(3). |  | 2009 | EC Task Force |
|  | b) | Develop and/or maintain standard communication protocols and cyber-security business practices as needed. |  |  |  |  |  |
|  |  | i) |  | Address the surety assessment findings on NAESB PKI standards. Status: Completed Item will be provided as a response to the U.S. DoE upon completion by the WGQ for their response to the findings. |  | 1st Q, 2008 | JISWG |
|  |  | ii) |  | Develop PKI standards for OASIS. Status: Not Started |  | 2009 | ESS/ITS |
|  |  | iii) |  | Develop PKI Standards for e-tagging (Develop Implementation Plan). Status: Underway eTagging items are linked to the transition of the Registry from NERC to NAESB. |  | 2nd Q 2009 | JISWG |
|  |  | iv) |  | Develop enhanced Electric Industry Registry (EIR), (R06027) Status: Underway |  | 2009 | NAESB Staff |
|  | c) | Develop needed business practice standards for organization/company codes for NAESB standards – and address current issues on the use of DUNs numbers. Status: Underway Common code usage is linked to the transition of the Registry from NERC to NAESB. |  |  |  | 2009 | NAESB Staff with WEQ support |
|  | d) | Develop business practice standards in support of FERC Order 717 Status: Not Started |  |  |  | 2nd Q, 2009 | ESS/ITS |
| 4 | Review and develop business practices standards to support e-Tariff program |  |  |  |  |  |  |
|  |  | Develop business practices as needed to support the e-Tariff program including submittal of tariffs and metadata. (Docket No RM05-1-000) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  |  |  | 1st Q, 2008 | Joint WEQ/WGQ e-Tariff Subcommittee |
| 5 | Review and develop business practices standards to Demand Response, Demand Side Management and Energy Efficiency Programs |  |  |  |  |  |  |
|  | Review and develop needed model business practices for a standardized method for quantifying benefits, savings, cost avoidance and/or the reduction in energy demand and usage derived from the implementation of demand side management and energy efficiency programs. This effort will include demand side response, energy efficiency programs and metering, including the 'curtailment service provider' program. |  |  |  |  |  |  |
|  | a) | Develop matrix and business practice standards for measurement and verification for demand response programs in ISO/RTO footprint areas. Status: Completed |  |  |  | 4th Q, 2008 | Joint WEQ/Retail DSM-EE Subcommittee |
|  | b) | Develop matrix and business practice standards for measurement and verification for demand response programs in non-ISO/RTO footprint areas. Status: Underway |  |  |  | TBD | Joint WEQ/Retail DSM-EE Subcommittee |
|  | c) | Develop preamble for business practice standards for measurement and verification for demand response and energy efficiency programs. Status: Underway |  |  |  | 2009 | Joint WEQ/Retail DSM-EE Subcommittee |
|  | d) | Develop glossary for business practice standards Status: Underway |  |  |  | 2009 | Joint WEQ/Retail DSM-EE Subcommittee |
|  | e) | Support retail development of matrix and model business practice standards for measurement and verification for demand response programs Status: Underway |  |  |  | 2009 | Joint WEQ/Retail DSM-EE Subcommittee |
|  | f) | Develop business practice standards to measure and verify energy reductions that are made to comply with a Renewable Portfolio Standard that included energy efficiency or a stand-alone Energy Efficiency Portfolio Standard. Status: Not Started |  |  |  | Phase 2 | Joint WEQ/Retail DSM-EE Subcommittee |
|  | g) | Develop business practice standards to factor Demand Control and Energy Efficiency programs into reliability / supply decisions at the wholesale level for generation and transmission planning and operations. Status: Not Started |  |  |  | Phase 2 | Joint WEQ/Retail DSM-EE Subcommittee |
|  | h) | Develop business practice standards for cap and trade programs for green house gas Status: Not Started |  |  |  | Phase 2 | Joint WEQ/Retail DSM-EE Subcommittee |
| 6 | Maintain existing body of Version 1 standards |  |  |  |  |  |  |
|  | a) |  | Review/revise WEQ 006 to remove/revise mandatory requirements for Interconnection Time Monitor (R07019) Status: Completed Published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  |  | 2nd Q, 2008 | BPS |
|  | b) |  | Develop a NAESB time and inadvertent management business practice that provides additional inadvertent payback options and improved time control (R07020) Status: Complete |  |  | 3rd Q, 2008 | BPS |
|  | c) |  | Make consistency changes to Version 1.0 standards as directed by the WEQ Leadership Committee on December 12, 2007 (R08001 – BPS, ESS/ITS, R08002 - ESS/ITS, R08003 - ESS/ITS - BPS, R08004, R08005 - ESS/ITS) |  |  |  |  |
|  |  |  | 1) | OASIS Consistency Changes (R08001, R08002, R08003, R08005) Status: Not Started |  | 2009 | ESS/ITS |
|  |  |  | 2) | Gas / Electric Communication Consistency Changes (R08004) Status: Underway |  | 2009 | BPS |
|  | d) |  | Modify WEQ-001 to reflect in the definition of certain ancillary services that such ancillary services may be provided by non-generation resources such as demand resources. (http://www.naesb.org/pdf3/weq_ec051308w2.doc) Status: Completed To be published in Version 002, September 30, 2008 and forwarded to the FERC as part of the Version 002 filing, August 29, 2008. |  |  | July 2008 | BPS, ESS/ITS |
|  | e) |  | Modify NAESB definitions to address internal inconsistencies and inconsistencies with the NERC glossary, (http://www.naesb.org/pdf3/weq_ec051308w3.doc) Status: Underway Subcommittee co-chairs are developing WEQ-000 Definition of Terms/Acronyms to replace definitions being included in each NAESB Business Practice. |  |  | 1st Q, 2009 | BPS, SRS, ESS/ITS |
|  | f) |  | Review and evaluate whether to cutoff or put a size limit on the entities for which the standards apply Status: Completed After review of FERC Order 676, the subcommittee determined this annual plan item was outside of NAESB’s scope. Waivers for standards based on an entity’s size should be addressed by FERC rather than through standards at NAESB. |  |  | 3rd Q, 2008 | SRS |
|  | g) |  | Investigate and review possible modifications to the WGQ Intraday Nominations, Confirmation Scheduling, and Gas Day standards, including possible standards for coordination of wholesale electric and wholesale gas scheduling. (R03031, R03031 revised, Interim Report, Final Report) Status: Completed The subcommittee reviewed the standards request and documentation developed by the Gas Electric Coordination Task Force and determined no additional work was required. The subcommittee approved a “no action” recommendation to close out this standards request. |  |  | 3rd Q, 2008 | SRS |
|  | h) |  | Develop standards to allow for registered Market Operators to request changes to the Market Level profile of Implemented Interchange (R06006) Status: Underway This request may be more of a clean-up in nature as it was requested in May 2006 but has not been addressed or presented as completed with the requisite documentation. |  |  | 1st Q 2009 | JISWG |
|  | i) |  | Modify the timing chart for the Western Interconnection in WEQBPS-006 to an initiation of manual time error at +/-5 seconds. (R06010) Status: Completed The BPS developed a No Action recommendation for this request since the scope of the request had been addressed through a minor correction in 3rd Quarter 2006. |  |  | 3rd Q, 2008 | BPS |
|  | j) |  | Develop a standard mechanism to implement a “RECALL” of transmission capacity from an existing confirmed transmission service reservation/Specify the technical requirements for implementation of a new OASIS request type, RECALL. (R07001) Status: Completed This request was originally assigned to the ESS/ITS in February 2007. |  |  | 3rd Q, 2008 | ESS/ITS |
|  | k) |  | Clarify the S&CP implementation of the DEFERRAL request. (R07003) Status: Completed This request was originally assigned to the ESS/ITS in February 2007. |  |  | 3rd Q, 2008 | ESS/ITS |
|  | l) |  | Develop business practice and technical standards for assigning, tracking, and limiting rollover rights. (R07004) Status: Completed This Standards Request was assigned to the ESS/ITS in February 2007. |  |  | 3rd Q, 2008 | ESS/ITS |
|  | m) |  | Update the Timing Table to Reflect the Categories (On-time, Late, After-the-fact, and Pre-late) used in the latest E-Tag Specification with respect to receipt of an Arranged Interchange (RFI). (R07007) Status: Completed |  |  | 4th Q, 2008 | JISWG |
|  | n) |  | Consistent with ¶51 of FERC Order No. 890-A, add AFC and TFC values to the “System_Attribute” data element of the NAESB Standard WEQ-003: OASIS S&CP Data Dictionaries. (R08011) Status: Not Started This Standards Request was assigned to the ESS/ITS in May 2008. |  |  | 2009 | ESS/ITS |
|  | o) |  | Provide for Enhanced Granularity for Public Utilities in Identifying Critical Operational Flow Orders. (R08020) Status: Not Started. This Standards Request was assigned to the BPS in August 2008. |  |  | 2009 | BPS jointly with WGQ BPS |

| NORTH AMERICAN ENERGY STANDARDS BOARD 2008 WEQ Annual Plan Approved by the Board of Directors on October 20, 2008 Reviewed by Subcommittee, Working Group, and Task Force Co-Chairs as of November 14, 2008 |  |
| --- | --- |
| PROVISIONAL ITEMS |  |
| 1 | Develop and or modify business practices related to support of NERC effort on the NERC Resources and Transmission Adequacy and Inadvertent Interchange Data Standards BAL-006 revisions. Status: In review of the NERC development effort, Balancing Authority Controls (Project 2007-05), with Mr. Akens (TVA, NERC Drafting Team Leader) and Mr. Rodriquez (NERC Manager, Business Practice Coordination), it was determined that no changes would be required to NAESB standards. As such, NAESB leadership is not at this time determining if any development would be undertaken, which would then initiate a joint development effort. A letter to this effect was sent to NERC management. This assessment may however change as the NERC drafting team proceeds further in its development, so the provisional item remains on the 2008 WEQ Annual Plan. |
| 2 | Develop business practice standards as requested by the regional and state advisory groups. |
| 3 | Develop business practice standards as related to the Effectiveness Study of Competitive Wholesale Markets (Congressional Mandate), Electric Energy Market Competition Task Force, Docket No. AD05-17-000, issued by the FERC on October 13, 2005. |
| 4 | Develop and/or maintain business practice standards to support gas-electric interdependencies |
|  | - Respond to requests as received that are related to Docket No. RM05-28-000. |
|  | - Respond directives related to the conclusions of the NAESB reports submitted in FERC Order No. 698, Docket Nos. RM05-5-001 and RM96-1-027. |
| 5 | Develop business practices for allocating capacity among requests received during a submittal window Order 890-A (Docket Nos. RM05-17-001, 002 and RM05-25-001, 002 - Paragraph 805). |
| 6 | Determine any needed NAESB action in support of the Interchange Distribution Calculator (IDC) and develop any necessary standards. |

Wholesale Electric Quadrant

Executive Committee (WEQ EC)

Standards Review Subcommittee (SRS)

Interpretations Subcommittee

Electronic Scheduling Subcommittee (ESS)

Information Technology Subcommittee (ITS)

Joint Interchange Scheduling Working Group

(JISWG)

Scoping

Task Forces & Working Groups

Development

E-Tariff Joint WEQ/WGQ Subcommittee

DSM-EE Retail/WEQ Subcommittee

Business Practices Subcommittee (BPS)

NAESB WEQ EC and Subcommittee Leadership:

Executive Committee:  Kathy York (WEQ EC Chair) and Clay Norris (WEQ EC Vice Chair)

Standards Review Subcommittee:  Narinder Saini, Ed Skiba

Interpretations Subcommittee:  Robert Schwermann

Business Practices Subcommittee & Task Forces: Jim Busbin (TLR), Ed Skiba

Electronic Scheduling Subcommittee/Information Technology Subcommittee & Task Forces: Paul Sorenson, J.T. Wood, Marcie Otondo

Joint Interchange Scheduling Working Group (JISWG):  Bob Harshbarger (NAESB), Jim Hansen (NERC)

e-Tariff Joint WEQ/WGQ Subcommittee (e-Tariff):  Jane Daly (WEQ), Keith Sappenfield (WGQ)

DSM-EE Joint Retail/WEQ Subcommittee: Ruth Kiselewich and David Koogler (Retail), Roy True and Paul Wattles (WEQ)

End Notes WEQ 2008 Annual Plan:

? Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.

The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the annual plan document.

For additional information, please see:  http://www.naesb.org/pdf3/weq_bps100407w4.ppt for Phase II changes and http://www.naesb.org/pdf2/weq_bps070907w4.doc for Phase III changes.

Joint Development Procedure is to be used by the NERC TLR Drafting Team and NAESB BPS.

? For additional information, please see comments submitted by PJM and MISO for this Annual Plan Item:  http://www.naesb.org/pdf3/weq_aplan102907w1.pdf.

Joint Development Procedure is to be used by the NERC TLR Drafting Team and NAESB BPS.

The June 1, 2008 dates included in this Annual Plan Item are assigned as a result of FERC extending deadlines to both NERC and NAESB on ATC related Order No. 890 items.