[image: image2.png]0

I

0




North American Energy Standards Board

1301 Fannin, Suite 2350, Houston, Texas 77002

Phone:  (713) 356-0060, Fax:  (713) 356-0067, E-mail: naesb@naesb.org


Home Page: www.naesb.org

	NORTH AMERICAN ENERGY STANDARDS BOARD

Proposed 2008 WEQ Annual Plan Prepared October 29, 2007
Presented to the WEQ Executive Committee on November 6, 2007


	
	Item Description
	Completion

	Assignment


	1
	Develop business practices standards as needed to complement reliability standards

	
	Develop business practice standards to support and complement NERC reliability standards, NERC policies and NERC standards authorization requests (SARs) using the NERC/NAESB Coordination Joint Standards Development Process as appropriate.  Current NAESB activities underway to develop business practice standards that are supportive of this annual plan item are: 

	
	a)
	Make version 2 changes to business practices as requested.
	Ongoing
	BPS

	
	
	i)
	Make changes to business practices as related to inclusion of the NERC Reliability Functional Model functional model entities as NERC undertakes the same efforts.

Status:  No requests.
	As requested
	BPS

	
	
	ii)
	Continuous support of TLR Procedure in alignment with NERC efforts on TLR Phase II and Phase III which would be included in version 2 development.

Status: Ongoing as NERC makes changes.
	Ongoing
	BPS


	
	b)
	Develop business practices to support Coordinate Interchange – R05020 “Include a guideline for rounding schedules with partial mWh's in the coordinate interchange business practice WEQ BPS-002-000”

Status: Underway.
	4th Q, 2007
	BPS, 
JISWG

	
	c)
	Operate Within Limits (R03017) as coordinated with the NERC schedule on the same development for reliability standards
	
	

	
	
	i)
	Review the need to develop business practice standards to support Operate Within Limits (R03017)
	2nd Q, 2008
	SRS

	
	
	ii)
	Develop business practice standards to support Operate Within Limits (R03017)
	4th Q, 2008
	BPS

	
	
	

	
	
	

	
	d)
	
Prepare recommendations for future path for TLR in concert with NERC, which may include alternative congestion management procedures
 

	4th Qtr 2008
	BPS, ESS-ITS


	
	
	
	

	
	

	
	
	
	

	
	

	
	e)
	Determine any needed NAESB action in support of the Interchange Distribution Calculator (IDC) and develop any necessary standards.

Status: Not Started.
	4th Q, 2008
	BPS

	
	
	
	
	

	
	
	
	
	

	
	
	

	
	

	2
	Develop business practice standards in support of the FERC RM05-25-000 and RM05-17-000 (OATT Reform)

	
	a)
	Develop version 1 business practice standards to better coordinate the use of the transmission system among neighboring transmission providers.  Such business practice standards would be based on recommendations from NERC's Long Term ATC/AFC Task Force and would involve revised procedures for the ATC calculation and/or revised protocols as determined by the final order.

Status: Underway using joint standards development process with NERC.  Request R050004 was expanded to include the OATT NOPR items (NOPR, Docket Nos. RM05-25-000 and RM05-17-000, “Preventing Undue Discrimination and Preference in Transmission Services”, issued May 19, 2006).
	
	

	
	
	
	

	
	

	
	
	i)
	Group 1: Conditional Firm, Annotations For ATC; Load Forecast And Actual Load; Re-Bid Of Partial Service; And Preconfirmation Priority

Status: Underway
	3rd Q, 2007

	ESS/ITS

	
	
	ii)
	Group 2:  Metrics; Redispatch Cost Posting

Status:  Not Started
	4th Q, 2007
	ESS/ITS

	
	
	iii)
	Group 3:  Network Service On OASIS

Status:  Not Started
	4th Q, 2007
	ESS/ITS

	
	
	iv)
	Group 4:  Pre-Emption; Request No. R05019; and Revisions to Standard 9.7

Status:  Not Started
	1st Q, 2008
	ESS/ITS

	
	
	v)
	Group 5:  Paragraph 1377

Status:  Not Started
	1st Q, 2008
	ESS/ITS

	
	
	vi)
	Group 6:  Miscellaneous (Paragraphs 1390 and 1627 of Order 890)

Status:  Not Started
	2nd Q, 2008
	ESS/ITS

	
	b)
	Develop the needed business practices as companion to the NERC standards for ATC related efforts.
	
	

	
	
	i)
	Develop standards to support existing Request No. R05004.

Status:  Underway
	4th Q, 2007
	BPS/ESS

	
	
	ii)
	Develop Business Practice Standards for Existing Transfer Capability (ETC)
	TBD
	BPS/ESS

	
	
	
	· Develop the Business Practice Standards complementary to NERC Reliability Standards for Existing Transfer Capability (ETC) to create a “consistent approach for determining the amount of transfer capability a transmission provider may set aside for its native load and other committed uses”, including the elements of ETC for full implementation of the NERC MOD-001 reliability standard.  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development.
Status:  Not Started.
	
	

	
	
	
	· Business practice standards for accounting for counterflows.  These standards will be included in the ATC business practice standards.  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development.

Status:  Underway
	
	

	
	
	iii)
	Capacity Benefit Margin (CBM) Business Practices 

Some of the Completion dates for these items may be changed if NERC timelines for Order 890 are changed:

	
	

	
	
	
	· Business practice standards to set forth “how the CBM value shall be determined, allocated across transmission paths, and used” and how transmission providers will “reflect the set-aside of transfer capability as CBM in the development of the rate for point-to-point transmission service.”  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development.

Status: Underway.
	TBD
	BPS/ESS

	
	
	
	· Business practice standards that include an OASIS mechanism to “allow for auditing of CBM usage.”  
The business practices developed to address this item will not require to coordination with the NERC Order 890 reliability standards development.
Status:  Underway.
	4th Q, 2007
	BPS/ESS

	
	
	
	· Any additional business practice standards needed to complement the NERC CBM reliability standards (MOD004) created as a result of this effort. 
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development.

Status:  Underway
	TBD
	BPS/ESS

	
	
	iv)
	Transmission Reliability Margin Business Practices:
Some of the Completion dates for these items may be changed if NERC timelines for Order 890 are changed:
	
	

	
	
	
	· Transmission Reliability Margin (TRM):   Business Practice Standards to complement the NERC reliability standards for TRM.  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development.
Status:  Underway
	TBD
	BPS/ESS

	
	
	
	· The business practice standards will include specification of the appropriate uses of TRM and when transmission providers may set aside TRM.  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development
	TBD
	BPS/ESS

	
	
	
	· Any additional business practice standards needed to complement the NERC TRM reliability standards (MOD008) created as a result of this effort.  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development
Status:  Underway
	TBD
	BPS/ESS

	
	
	v)
	Business Practice Standards for ATC and AFC Calculation Methodologies to complement the NERC reliability standards created for ATC and AFC Methodologies (NERC MOD001 (Available Transfer Capability); NERC MOD028 (Network Response Available Transfer Capability); NERC MOD029 (Rated System Path Available Transfer Capability); and NERC MOD030 (Flowgate Network Response Available Transfer Capability)):
Some of the Completion dates for these items may be changed if NERC timelines for Order 890 are changed:

	4th Q, 2007

	BPS/ESS

	
	
	
	· Business practice standards to address  the frequency and posting requirements for all ATC components that are complementary to the related NERC reliability standards.  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development.
	
	

	
	
	
	· Business practice standards for data exchange for ATC modeling complementary to the related NERC reliability standards including any OASIS posting requirements to achieve the data exchange.  
The business practices developed to address this item will require to coordination with the NERC Order 890 reliability standards development.

	
	

	
	
	
	· Business practice standards that will set forth how transmission providers will post “explanations of the reason for a change in monthly and yearly ATC values on a constrained path.”  The standards will include a requirement that that the transmission provider posts the reason for the change in a narrative form.  The posted information will include “the (1) specific events which gave rise to the change and (2) new values for ATC on that path (as opposed to all points on the network).”  
The business practices developed to address this item will not require to coordination with the NERC Order 890 reliability standards development.
	
	

	
	
	
	· Business practice standards for posting on OASIS of the “underlying load forecast assumptions for all ATC calculations”.  
The business practices developed to address this item will not require to coordination with the NERC Order 890 reliability standards development
	
	

	
	
	
	· Business practice standards for posting on OASIS of the “actual daily peak load for the prior day.”  
The business practices developed to address this item will not require to coordination with the NERC Order 890 reliability standards development
	
	

	
	
	vi)
	Business practice standards to complement NERC reliability standards for Transfer Capability in response to new NERC Supplemental SAR:  Revisions to Existing Standards MOD001-MOD009, FAC12-13
This item was added as a result of the Supplemental SAR NERC created in case additional business practices are needed as a result of the work on this SAR by NERC.  It does not have a cite in Order 890.  This item will require coordination with the NERC Order 890 reliability standards development.
Status:  Underway

	TBD
	BPS/ESS

	
	
	vii)
	Business practice standards to set forth the procedure for input on TTC and ATC methodologies and values.  (During the Order 890 NERC and NAESB joint standards development effort, it was determined that the standards contained in MOD003 should be business practice standards instead of reliability standards.  NERC has requested that NAESB adopt the standards as business practices via correspondence to Ms. McQuade, NAESB President.)

This item will require coordination with the NERC Order 890 reliability standards development because the language to address this item is contained within a draft standards that addresses items that are dependent on NERC deliverables, i.e., the requirements to create an “ATC Information Link” on OASIS.  There is no Order 890 cite for this item.

Status:  Underway
	TBD
	BPS/ESS

	
	c)
	Develop version 1 business practice standards to support transparency reporting and related functions that may be required as a result of the final order.

Status: Not Started.
	TBD
	BPS/ESS

	3
	Develop business practices standards to improve the current operation of the wholesale electric market and develop and maintain business practice and communication standards for OASIS and Electronic Scheduling

	
	a)
	Develop and/or maintain business practice standards as needed for OASIS and electronic scheduling. Specific items to address include:

	
	
	i)
	Develop OASIS S&CP changes to support OASIS business practices.
Status: Dependent on development of OASIS business practices.
	Ongoing
	ESS/ITS

	
	
	
	
	

	
	

	
	
	
	
	

	
	

	
	
	ii)
	Network Services: Determine and develop needed business practice standards or other support is needed to support use of OASIS for Network Service transactions (R04006E).

Status: Underway.
	4th Q, 2007
	ESS/ITS

	
	
	iii)
	Registry (TSIN):  Determine and develop needed business practice standards to support the registry functions currently supported by NERC (R04037).

Status: Underway.
	4th Q 2008
	JISWG

	
	
	
	1)
	Work with the NAESB counsel to develop a confidentiality agreement
	
	JISWG

	
	
	
	2)
	Transition the TSIN Registry from NERC to NAESB.
	
	JISWG

	
	
	
	3)
	Review and correct the Coordinate interchange Business Practice Standard as noted during the development of the e-Tag 1.8 development process.
	
	JISWG

	
	
	
	

	
	

	
	
	v)
	Document procedures used to implement the displacement/interruption terms of the Pro Forma tariff (R05019).

Status: Not Started.(Related to request R05004)
	4th Q, 2007
	ESS/ITS

	
	
	vi)
	Make incremental enhancements to OASIS as an outgrowth of the NAESB March 29, 2005 conference on the future of OASIS (R05026).

Status: Underway.  Scoping statement completed by SRS, assignments made, and clarifications requested from the submitter.
	2008
	Various

	
	
	vii)
	Respond to issues in FERC Order No. 676 (Docket No. RM05-5-000) – NAESB WEQ Standards 001 9.7, (paragraph 51 of the order).

Status: Underway.  Assigned to group 4, reference 2007 WEQ AP item 2(a)(v)
	1st Q, 2008
	ESS/ITS

	
	b)
	Develop and/or maintain standard communication protocols and cyber-security business practices as needed.

	
	
	i)
	Address the surety assessment findings on NAESB PKI standards.

Status: Complete, will be provided as a response to the U.S. DoE upon completion by the WGQ for their response to the findings.
	1st Q, 2008
	JISWG

	
	
	ii)
	Develop PKI standards for OASIS.

Status: Not Started. 
	4th Q, 2007
	ESS

	
	
	iii)
	Develop PKI Standards for e-tagging.

Status: Underway.
	4th Q, 2007
	JISWG

	
	
	iv)
	Develop enhanced Electric Industry Registry (EIR), (R06027)

Status: Underway.
	4th Q, 2007
	JISWG

	
	c)
	Develop needed business practice standards for organization/company codes for NAESB standards – and address current issues on the use of DUNs numbers.

Status: Underway.
	4th Q, 2007
	NAESB Staff with WEQ support

	
	

	
	
	

	
	

	
	
	

	
	

	4
	Review and develop business practices standards to support e-Tariff program

	
	
	Develop business practices as needed to support the e-Tariff program including submittal of tariffs and metadata. (Docket No RM05-1-000)

Status: Underway.
	1st Q 2008
	Joint WEQ/WGQ e-Tariff Subcommittee

	5
	Review and develop business practices standards to Demand Response, Demand Side Management and Energy Efficiency Programs

	
	
	Review and develop needed model business practices for a standardized method for quantifying benefits, savings, cost avoidance and/or the reduction in energy demand and usage derived from the implementation of demand side management and energy efficiency programs.  This effort will include demand side response, energy efficiency programs and metering, including the 'curtailment service provider' program.

	2008
	Joint WEQ/Retail DSM-EE Subcommittee

	
	a)
	Develop matrix and business practice standards for measurement and verification for demand response programs in ISO/RTO footprint areas.
Status: Underway
	
	

	
	b)
	Develop matrix and business practice standards for measurement and verification for demand response programs in non-ISO/RTO footprint areas.
Status: Underway
	
	

	
	c)
	Develop preamble for business practice standards for measurement and verification for demand response and energy efficiency programs.
Status:  Underway
	
	

	
	d)
	Develop glossary for business practice standards

Status:  Underway
	
	

	
	e)
	Support retail development of matrix and model business practice standards for measurement and verification for demand response programs
Status:  Underway
	
	

	
	f)
	Develop business practice standards to measure and verify energy reductions that are made to comply with a Renewable Portfolio Standard that included energy efficiency or a stand-alone Energy Efficiency Portfolio Standard. 
Status: Not Started
	
	

	
	g)
	Develop business practice standards to factor Demand Control and Energy Efficiency programs into reliability / supply decisions at the wholesale level for generation and transmission planning and operations.
Status: Not Started.
	
	

	
	h)
	Develop business practice standards for cap and trade programs for green house gas
Status: Not Started.
	
	

	PROVISIONAL ITEMS

	1
	Develop and or modify business practices related to support of NERC effort on the NERC Resources and Transmission Adequacy and Inadvertent Interchange Data Standards BAL-006 revisions.

	2
	Develop business practice standards as requested by the regional and state advisory groups.

	
	

	3
	Develop business practice standards as related to the Effectiveness Study of Competitive Wholesale Markets (Congressional Mandate), Electric Energy Market Competition Task Force, Docket No. AD05-17-000, issued by the FERC on October 13, 2005.

	
	

	4
	Develop and/or maintain business practice standards to support gas-electric interdependencies

	
	· Respond to requests as received that are related to Docket No. RM05-28-000.

	
	· Respond directives related to the conclusions of the NAESB reports submitted in FERC Order No. 698, Docket Nos. RM05-5-001 and RM96-1-027.

	
	

	5
	Review Market System Back-Up existing language and review of existing back-up language

	6
	Review and Evaluation of whether to cutoff or put a size limit on the entities for which the standards apply



[image: image1]
NAESB WEQ EC and Subcommittee Leadership:

Executive Committee:  Kathy York (WEQ EC Chair) and Clay Norris (WEQ EC Vice Chair)

Standards Review Subcommittee:  Raj Rana, Narinder Saini

Interpretations Subcommittee:  Robert Schwermann


Business Practices Subcommittee & Task Forces: Kathy York & Jim Busbin
Electronic Scheduling Subcommittee/Information Technology Subcommittee & Task Forces: Paul Sorenson, J.T. Wood, Marcie Otondo
Joint Interchange Scheduling Working Group (JISWG):  Bob Harshbarger (NAESB), Jim Hansen (NERC)

e-Tariff Joint WEQ/WGQ Subcommittee (e-Tariff):  Jane Daly (WEQ), Keith Sappenfield (WGQ)

DSM-EE Joint Retail/WEQ Subcommittee: Ruth Kiselewich and David Koogler (Retail), Roy True and Paul Wattles (WEQ)

Wholesale Electric Quadrant


Executive Committee (WEQ EC)








Standards Review Subcommittee (SRS)








Business Practices Subcommittee (BPS)








Business Practices Interpretations Subcommittee (BPS)








Electronic Scheduling Subcommittee (ESS)








Information Technology Subcommittee (ITS)





Joint Interchange Scheduling Working Group


(JISWG)








Scoping





Task Forces & Working Groups








Development








E-Tariff Joint WEQ/WGQ Subcommittee








DSM-EE Retail/WEQ Subcommittee








� For additional information, please see:  � HYPERLINK "http://www.naesb.org/pdf3/weq_bps100407w4.ppt" �http://www.naesb.org/pdf3/weq_bps100407w4.ppt� for Phase II changes and � HYPERLINK "http://www.naesb.org/pdf2/weq_bps070907w4.doc" �http://www.naesb.org/pdf2/weq_bps070907w4.doc� for Phase III changes


� Joint Development Procedure to be used by the NERC TLR Drafting Team and NAESB BPS


� For additional information, please see comments submitted by PJM and MISO for this Annual Plan Item:  � HYPERLINK "http://www.naesb.org/pdf3/weq_aplan102907w1.pdf" �http://www.naesb.org/pdf3/weq_aplan102907w1.pdf�


� Joint Development Procedure to be used by the NERC TLR Drafting Team and NAESB BPS and ESS/ITS





End Notes:





� Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed so as to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.


� The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the annual plan document.


� The chairs of the ESS/ITS working on Order 890 OASIS issues modified the completion date from 3rd Quarter 2007 to 4th Quarter 2008 on 8-21-07.


�   The BPS/ESS groups working on Order 890 modified the completion date from 3rd to 4th Quarter 2007 for item 2(b)(ii) addressing ETC business practices development after the WEQ EC approved the other suggested changes in the WEQ 2007 Annual Plan on 8-14-07.


� The BPS/ESS groups working on Order 890 modified the completion date from 3rd to 4th Quarter 2007 for item 2(b)(iv) addressing TRM business practices development after the WEQ EC approved the other suggested changes in the WEQ 2007 Annual Plan on 8-14-07.


� The BPS/ESS groups working on Order 890 modified the completion date from 3rd to 4th Quarter 2007 for item 2(b)(v) addressing ATC and TTC business practices development related to NERC MOD001, MOD028, MOD029 and MOD030 after the WEQ EC approved the other suggested changes in the WEQ 2007 Annual Plan on 8-14-07.





Proposed 2008 NAESB Wholesale Electric Quadrant Annual Plan

Presented to the WEQ Executive Committee on November 6, 2007 

Page 7 of 11

