[image: image2.png]0

I

0




North American Energy Standards Board

1301 Fannin, Suite 2350, Houston, Texas 77002

Phone:  (713) 356-0060, Fax:  (713) 356-0067, E-mail: naesb@naesb.org


Home Page: www.naesb.org

North American Energy Standards Board

1301 Fannin, Suite 2350, Houston, Texas 77002

Phone:  (713) 356-0060, Fax:  (713) 356-0067, E-mail: naesb@naesb.org


Home Page: www.naesb.org

	NORTH AMERICAN ENERGY STANDARDS BOARD

2010 Annual Plan for the Wholesale Gas Quadrant as Approved by the Board of Directors on March 25, 2010


	Item Description
	Completion

	Assignment


	1.  Gas-Electric Interdependency

	
	Respond to directives of FERC Order No. 698 issued 6-25-07, Docket Nos. RM05-5-001 and RM96-1-027 as related to the NAESB reports submitted in Docket No. RM05-28-000:

	
	a.
	Provide for Enhanced Granularity for Public Utilities in Identifying Critical Operational Flow Orders. (R08020)

Status: Completed
	4th Q, 2009
	BPS, IR/Tech jointly with WEQ BPS

	2.  Promotion of a More Efficient Capacity Release Market
	
	

	
	Review FERC Order Nos. 712 and 712A and modify NAESB standards as appropriate (Docket Nos. RM08-1-000, RM08-1-001). 

	
	a.
	Review recent FERC order on flow-through of Discounted or Negotiated Rates (Docket No. RP09-70 et al, October 15, 2009) and develop business practice standards as appropriate
Status: Not Started
	2nd Q, 2010
	BPS/Interpretations

	3.  Capacity Release EDI Review
	
	

	
	Review capacity release transactions upload and related responses to determine suitability for EDI

	
	a.
	Develop Business Practice Standards as appropriate
Status: Underway
	2nd Q, 2010
	BPS

	
	b.
	Prepare fully staffed recommendation
Status: Underway (Adjustments may be made to Completion Dates based on report from Item 3.a)
	3rd  Q, 2010
	BPS, IR/Technical

	4.  Customer Security Administration
	
	

	
	Review and develop standards as appropriate to support Customer Security Administration Standards (Comment Submittal, 10-29-07)

Status:  Not started (Scoping to take place  2nd Q, 2010 after which a Completion Date will be set)
	2010
	BPS

	5.  Electronic Delivery Mechanisms
	
	

	
	Review minimum technical characteristics in Appendices B, C, and D of the WGQ QEDM Manual, and make changes as appropriate. 

Status:  Not Started
	2nd Q, 2010
	EDM

	6.  FERC Strategic Plan FY2009-2014

	
	a.
	For the FERC Strategic Plan, under the section “Promote efficient design and operation of natural gas facilities”, review and develop standards as needed to support EBB posting requirements regarding waste heat feasibility (NAESB Standard No. 4.2.23)
Status:  Underway
	2nd  Q, 2010
	BPS

	7.  Common Codes

	
	a.
	Review common code specifications for common location codes and determine if changes are necessary to the existing specifications to support both intrastate and interstate pipelines
Status:  Not Started
	4th Q, 2010
	BPS

	Program of Standards Maintenance & Fully Staffed Standards Work


	
	Business Practice Requests 
	Ongoing
	Assigned by the EC


	
	Continue review against plan for migration to ANSI ASC X12 new versions as needed and coordinate such activities with DISA.
	Ongoing
	ANSI X12 Subcommittee

	
	Information Requirements and Technical Mapping of Business Practices
	Ongoing
	Assigned by the EC3

	
	Interpretations for Clarifying Language Ambiguities 
	Ongoing
	Assigned by the EC3

	
	Maintenance of Code Values and Other Technical Matters
	Ongoing
	Assigned by the EC3

	
	Maintenance of Contracts Standards
	As Requested
	Contracts Subcommittee

	
	Maintenance of eTariff Standards
	As Requested
	Assigned by the EC3

	Provisional Activities

	1
	Review and develop standards as needed, related to Docket No.  RM09-2-000, (Contract Reporting Requirements of Intrastate Natural Gas Companies).

	2
	Review and develop standards as needed related to the FERC Strategic Plan 2009-2014



[image: image1]
NAESB 2010 WGQ EC and Subcommittee Leadership: 
Executive Committee:  Jim Buccigross, Chair and Dale Davis, Vice-Chair

Business Practices Subcommittee:  Kim Van Pelt, Valerie Crockett, Steve Abbey, Mike Novak and Richard Smith

Information Requirements Subcommittee:  Dale Davis

Technical Subcommittee:  Mike Stender, Kim Van Pelt
Contracts Subcommittee:  Keith Sappenfield

Electronic Delivery Mechanism Subcommittee:  Leigh Spangler, Christopher Burden

Interpretations Subcommittee:  Paul Love
Joint WEQ/WGQ e-Tariff Subcommittee:  Keith Sappenfield, Jane Daly

Interpretations Subcommittee





The translation of business practices to usable uniform business transactions is accomplished through the definition of information requirements for the data, and mapping of that data into specific electronic transactions.  This translation is performed by IR and Technical subcommittees and completes the standards development process, often referred to as “full staffing.”  Both IR and Technical work in tandem to complete this crucial technical implementation activity.  Until these steps have been completed, the process is incomplete, and in many cases, the business practices cannot be used.





Practices


Development





Task Forces & Working Groups





Technical


Implementation





ANSI X12 Subcommittee





Electronic Delivery Mechanism Subcommittee (EDM)








Technical Subcommittee





Information Requirements Subcommittee (IR)








Joint WEQ/WGQ e-Tariff Subcommittee





Contracts Subcommittee





Business Practices Subcommittee (BPS)





Wholesale Gas Quadrant


Executive Committee (WGQ EC)














End Notes, WGQ 2010 Annual Plan:


� Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.


� The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the annual plan document.


� The EC assigns maintenance of existing standards on a request-by-request basis.





NAESB 2010 WGQ Annual Plan approved by the Board of Directors on March 25, 2010
Page 1 of 4  

NAESB 2010 WGQ Annual Plan as approved by the Board of Directors on March 25, 2010
Page 4 of 4

