| NORTH AMERICAN ENERGY STANDARDS BOARD 2010 ANNUAL PLAN for the RETAIL GAS and ELECTRIC QUADRANTS As Approved by the NAESB Board of Directors on September 23, 2010 With Proposed Changes from the Retail ECs |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Item Number & Description |  |  |  | Completion | Assignment |
| 1. |  | Develop Technical Electronic Implementation Standards and Data Dictionaries – Book 10: Customer Enrollment, Drop and Account Information Change |  |  |  |  |  |
|  |  | a.. | For the Distribution Company Registration Model Registration Agent Model Status: Not Started |  |  | 2011 | TEIS |
| 2. | Develop NAESB Certification checklist criteria for Retail Quadrants to be used in the NAESB Certification Program. The certification checklist may address test scripts, a checklist of items to be tested, data connectivity for test scripts and EDM testing. Status: Not Started. Dependent upon publication of Version 2.0 at a minimum, but more dependent upon completion of Customer Choice efforts, expected 1st Q 2011 at the earliest. |  |  |  |  | 2011 | Ad Hoc EC Certification Group |
| 3. | Review and develop business practices standards to Demand Response, Demand Side Management and Energy Efficiency Programs Review and develop needed model business practices for a standardized method for quantifying benefits, savings, cost avoidance and/or the reduction in energy demand and usage derived from the implementation of demand side management and energy efficiency programs. This effort will include demand side response, energy efficiency programs and metering, including the 'curtailment service provider' program. The wholesale and retail demand response work groups and the Smart Grid Standards Subcommittees should actively and timely communicate and coordinate work products to ensure consistency between the three work groups. Each work group should take into account the work products developed by the other. |  |  |  |  |  |  |
|  | a. |  | Develop glossary for business practice standards Status: Ongoing |  |  | Ongoing | Joint WEQ/REQ DSM Subcommittee |
|  | b. |  | Develop business practice standards used to measure and verify reductions in energy and demand from energy efficiency in wholesale and retail markets. This includes developing business practice standards to measure and verify energy reductions that are made to comply with a Renewable Portfolio Standard that included energy efficiency or a stand-alone Energy Efficiency Portfolio Standard. Status: Underway |  |  | 1stQ, 2011 | Joint WEQ/REQ DSM-EE Subcommittee |
|  | c. |  | Support the second phase of retail development of model business practice standards for demand response programs Status: Complete |  |  | 4th Q, 2010 | REQ Section of the Joint WEQ/REQ DSM Subcommittee |
|  | d. |  | Create common interfaces and data structures necessary for enrolling DR sites into a DR program (Request No. R10002) Status: Underway |  |  | 4th Q, 2010 | REQ Section of the Joint WEQ/REQ DSM Subcommittee with coordination with Smart Grid Standards Task Force and REQ BPS |
| 4. | Billing and Payments |  |  |  |  |  |  |
|  | a. |  | Develop Process Flows to be included as models in Book 3 – Billing and Payments Status: Completed |  |  | 2nd Q, 2010 | BPS |
|  | b. |  | If the development of Process Flows indicate a gap in the model business practices, then develop new model business practices to address the gap. Status: Completed |  |  | 2nd Q, 2010 | BPS |
| 5. | Model Business Practices User Guide |  |  |  |  |  |  |
|  | a. |  | Add a new section to Book 0 to describe what Books have been developed, how the Books are laid out, and revised the title of the Book to reflect the additions Status: Completed |  |  | 4th Q, 2010 | BPS |
|  | b. |  | Develop process flows to support the user’s guide Status: Not Started |  |  | 2011 | BPS |
| 6. | Additional Registration Agent Processes |  |  |  |  |  |  |
|  | a. |  | Review all existing Model Business Practices to determine if the Customer Information process is already covered, and if necessary develop any new Model Business Practices required Status: Completed |  |  | 1st Q, 2010 | BPS |
|  | b. |  | Review all existing Model Business Practices to determine if the disconnection and reconnection process is already covered, and if necessary develop any new Model Business Practices required. Status: Completed |  |  |  |  |
|  |  |  | i. |  | Create MBPs for disconnection/reconnection initiated by the supplier Status: Completed | 4th Q, 2009 | BPS |
|  |  |  | ii. |  | Create MBPs for disconnection/reconnection initiated by the distribution company Status: Completed | 4th Q, 2009 | BPS |
|  | c. |  | Review all existing Model Business Practices to determine if there are other Registration Agent Model processes not covered, and develop a prioritized list of those processes, if any. Status: Underway |  |  | 2011 | BPS |
|  | d. |  | Develop Model Business Practices and Process Flows for those Registration Agent Model processes on the prioritized list developed in (c) above, if any. Status: Underway |  |  | 2011 | BPS |
|  | e. |  | Develop Technical Electronic Implementation Standards and Data Dictionaries to support Model Business Practices of Book 14 – Service Requests, Disconnections and Reconnections in the registration Agent Model Status: Underway |  |  | 2011 | IR/TEIS |
|  | f. |  | Develop Technical Electronic Implementation Standards and Data Dictionaries to support any Model Business Practices developed in (d) above Status: Underway |  |  | 2011 | IR/TEIS |
| 7. | Supplier Certification Develop practices to register/certify new Suppliers. Status: Underway |  |  |  |  | 2011 | BPS |
| 8. | Supplier Marketing Practices Develop Model Business Practices providing for a “Consumer Disclosure Statement” to be presented to residential and small commercial customers describing the Supplier’s service offering and related contract provisions. This statement would also identify how certain Supplier-Customer interactions are conducted. Amongst the topics to be considered for inclusion on the statement would be the following: • the most important terms of the Supplier agreement, such as the contract’s term and termination fee provisions; • training and identification of Supplier marketing representatives; • protocols for Supplier in-person and telephone contacts with customers; • added measures for protecting non-English speaking customers; and • Processes for handling customer complaints and resolving disputes arising from Supplier marketing activities. Status: Underway |  |  |  |  | 1st Q, 2011 | BPS |
| 9. | Develop Smart Grid Wholesale and Retail Electric Standards |  |  |  |  |  |  |
|  | a. |  | Develop Requirements and Use Cases for PAP 03 – Pricing Model |  |  |  |  |
|  |  |  | i. |  | Phase 1 Status: Completed | 1st Q, 2010 | Joint WEQ/REQ SGS Subcommittee |
|  |  |  | ii. |  | Phase 2 Status: Completed | 4th Q, 2010 | Joint WEQ/REQ SGS Subcommittee |
|  | b. |  | Develop Requirements and Use Cases for PAP 04 – Scheduling Model |  |  |  |  |
|  |  |  | i. |  | Phase 1 Status: Completed | 1st Q, 2010 | Joint WEQ/REQ SGS Subcommittee |
|  |  |  | ii. |  | Phase 2 Status: Completed | 4th Q, 2010 | Joint WEQ/REQ SGS Subcommittee |
|  | c. |  | Develop Requirements and Use Cases for PAP 09 – Demand Response/Distributed Energy Resources |  |  |  |  |
|  |  |  | i. |  | Phase 1 Status: Completed | 1st Q, 2010 | REQ Section of the Joint WEQ/REQ SGS Subcommittee |
|  |  |  | ii. |  | Phase 2 Status: Completed | 4th Q, 2010 | REQ Section of the Joint WEQ/REQ SGS Subcommittee |
|  | d. |  | Develop standards to support PAP 10 – Standards Energy Usage Information |  |  |  |  |
|  |  |  | i. |  | Act as a convener (develop and implement a plan to expedite harmonized standards development and adoption within the associated standards bodies) and develop business practice standards as needed and assigned to NAESB for PAP 10 – Standard Energy Usage Information Status: Completed | 2nd Q, 2010 | Joint WEQ/REQ PAP 10 SGS Subcommittee |
|  |  |  | ii. |  | Develop Information Model and related business practices Status: Complete | 4th Q, 2010 | Joint WEQ/REQ PAP 10 SGS Subcommittee |
|  | e. |  | Develop standards to support inclusion of OpenADE requirements document into the NAESB Smart Grid standards (R10008), specifically to standardize the exchange of Energy Usage Information. Status: Underway |  |  | 1st Q, 2011 | REQ PAP 10 SGS Subcommittee Energy Services Provider Interface Task Force |
| 10. | Reserved (Items added under action item 6) |  |  |  |  |  |  |
| 11. | Master List of Defined Terms: Review the definitions of all Defined Terms in Book 0 – Master List of Defined Terms, including other Ratified Terms not yet published, and revise the definitions of all Defined Terms not specifically related solely to the competitive marketplace to broaden their applicability to conform to NAESB’s expanded scope. Status: Completed |  |  |  |  | 3rd Q, 2010 | Glossary |
| Program of Standards Maintenance & Fully Staffed Standards Work |  |  |  |  |  |  |  |
|  |  | Business Practice Requests |  |  |  | Ongoing | Assigned by the EC |
|  |  | Information Requirements and Technical Mapping of Business Practices |  |  |  | Ongoing | Assigned by the EC |
|  |  | Ongoing Interpretations for Clarifying Language Ambiguities |  |  |  | Ongoing | Assigned by the EC |
|  |  | Ongoing Maintenance of Code Values and Other Technical Matters |  |  |  | Ongoing | Assigned by the EC |
|  |  | Ongoing Development and Maintenance of Definitions |  |  |  | Ongoing | Glossary |
| Provisional Activities |  |  |  |  |  |  |  |
|  |  | Joint Effort: |  |  |  |  |  |
|  |  |  |  | Modify TPA as necessary. |  |  |  |
|  |  |  |  | Review security standards as may be deemed necessary, such as Public Key Infrastructure (PKI). |  |  |  |
|  |  |  |  | Review existing body of model business practices for consistency and develop or modify model business practices as needed. |  |  |  |
|  |  |  |  | Review and update the technical implementation of Book 3 – Billing and Payment |  |  |  |
|  |  | Retail Electric Quadrant Effort Only: |  |  |  |  |  |
|  |  |  |  | Retail Meter Data Validation, Editing & Estimating: Develop procedures for insuring the integrity and validity of retail customer metering data that is needed by utilities and suppliers for billing, etc. Issues related to unbundled or competitive metering are not to be considered. |  |  |  |
|  |  |  |  | Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market. Note: will need to be coordinated with the WEQ for the REQ. |  |  |  |
|  |  |  |  | Develop business practice standards for cap and trade programs for green house gas (See action item 6h). |  |  |  |
|  |  | Retail Gas Quadrant Effort Only: |  |  |  |  |  |
|  |  |  |  | Examine Wholesale Gas Quadrant Non-EDM Standards for applicability to retail business practices. |  |  |  |
|  |  |  |  | Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market. |  |  |  |

Retail Electric & Retail Gas

Quadrant Executive Committees

(REQ and RGQ ECs)

Business Practices Subcommittee (BPS)

Contracts Subcommittee (dormant)

Glossary Subcommittee

Retail Ad Hoc Texas Task Force (*)

Technical Electronic

Implementation Subcommittee (TEIS)

Model Business

Practice

Development

Task Forces & Working Groups

Technical

Standards

Development

Joint Retail/WEQ DSM-EE Subcommittee

Information Requirements Subcommittee (IR)

PAP 10 Smart Grid Standards Subcommittee (***)

Smart Grid Standards Development Subcommittee (**)

NAESB Retail Subcommittee Leadership:

Executive Committee:  Mike Novak, Chair (RGQ), Phil Precht, Chair (REQ)

Business Practices Subcommittee:  Phil Precht (RGQ), Dan Jones (REQ)

Information Requirements Subcommittee: Jennifer Teel (REQ)

Technical Electronic Implementation Subcommittee: TBD

Glossary Subcommittee:  Patrick Eynon (REQ)

DSM-EE Subcommittee: Ruth Kiselewich, David Koogler (REQ), Roy True (WEQ), and Paul Wattles (WEQ)

Retail Ad Hoc Texas Task Force: Debbie McKeever (REQ) and Susan Munson (REQ)

(*)  The Retail Ad Hoc Texas Task Force may draft MBPs, process flows, implementation guides and technical standards supportive of the Registration Agent.  The group is chaired by Debbie McKeever and Susan Munson.

(**)  The Smart Grid Standards Subcommittee is a joint group of the retail electric and wholesale electric quadrants with other standards development groups such as OASIS, CalConnect, FIX and UCAIug, and includes other groups.  Direction may be given from NIST, DoE or FERC and the group reports jointly to the NAESB Board Smart Grid Strategic Steering Committee and the REQ EC.  The group is chaired by Brent Hodges, Wayne Longcore, Joe Zhou and Robert Burke.

(***)  The PAP 10 Smart Grid Standards Subcommittee is a joint group of the retail electric and wholesale electric quadrants with other standards development groups such as OASIS, UCAIug, OpenADE, ZigBee, ASHRAE, EIS Alliance, NARUC and includes other groups.  Direction may be given from NIST, DoE or FERC and the group reports jointly to the NAESB Board Smart Grid Strategic Steering Committee and the REQ EC.  The group is chaired by Brent Hodges, Phil Precht, Cathy Wesley/Heather Sanders, Sharon Dinges, David Kaufman, Brad Ramsay, Tobin Richardson and Ed Koch.
The PAP 10 Smart Grid Standards Subcommittee has created a Energy Services Providers Interface Task Force led by Dave Mollerstuen of Tendril, Steve Van Ausdall of Xtensible and Chad Maglaque of Xtreme Consulting Group to address the OpenADE request R10008.

Retail 2010 Annual Plan End Notes:

? As outlined in the NAESB Bylaws, the REQ and RGQ will also address requests submitted by members and assigned to the REQ and RGQ through the Triage Process.

Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.

The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the annual plan document.

The DSM-EE subcommittee is expected to be split into several separate subcommittees to support concurrent development of separate standards sets.  The split is to take place at the end of May after which the assignments will be modified.

Energy efficiency may be a wholesale product, such as capacity. Energy efficiency in retail markets may be from individual energy efficiency measures at the project level or a portfolio of projects that make up an energy efficiency program.

This work is considered routine maintenance and thus the items are not separately numbered. The REQ and RGQ ECs will assign maintenance efforts on a request-by-request basis.

The ECs and the subcommittees can create task forces and working groups to support their development activities for development of model business practices and technical standards.