[image: image2.png]0

I

0




North American Energy Standards Board

1301 Fannin, Suite 2350, Houston, Texas 77002

Phone:  (713) 356-0060, Fax:  (713) 356-0067, E-mail: naesb@naesb.org


Home Page: www.naesb.org

North American Energy Standards Board

1301 Fannin, Suite 2350, Houston, Texas 77002

Phone:  (713) 356-0060, Fax:  (713) 356-0067, E-mail: naesb@naesb.org


Home Page: www.naesb.org

	NORTH AMERICAN ENERGY STANDARDS BOARD

2009 ANNUAL PLAN for the RETAIL GAS and ELECTRIC QUADRANTS
Adopted by the NAESB Board of Directors on March 26, 2009 with Suggested Retail EC Changes as of May 13, 2009

	
	Item Number & Description

	Completion

	Assignment



	1.
	Electronic Retail Billing.

	
	Develop Technical Electronic Implementation Standards and Data Dictionaries –  Book 9: Customer Billing and Payment Notification via Uniform Electronic Transactions, (R05016 and Attachment, submitted by Wal-Mart/J.C. Penney)
Status:  Complete
	2nd Q, 2009
	TEIS

	2.
	Develop Technical Electronic Implementation Standards and Data Dictionaries –  Book 8: Customer Information

Status:  Complete
	2nd Q, 2009
	TEIS

	3.
	Develop Technical Electronic Implementation Standards and Data Dictionaries –  Book 10: Customer Enrollment, Drop and Account Information Change (Non Texas Model)
Status:  Complete
	2nd Q, 2009
	TEIS

	4.
	Customer Inquiries

	
	a.
	Develop Model Business Practices and procedures for responding to customer inquiries directed to Distributors and/or Suppliers and for notification of the other party.
Status:  Complete
	2nd Q, 2009
	BPS

	
	b.
	Develop Technical Electronic Implementation Standards to support MBPs for customer inquiries directed to Distributors and/or Suppliers and for notification of the other party.
Status: Underway
	3rd Q, 2009
	IR/TEIS/Texas Task Force

	5.
	Develop NAESB Certification checklist criteria for Retail Quadrants to be used in the NAESB Certification Program.
Status:  Not Started.  Dependent upon publication of Version 1.1 at a minimum, but more dependent upon completion of Customer Choice efforts.
	4th Q, 2009
	Ad Hoc EC Certification Group

	6.
	Review and develop needed model business practices for a standardized method for quantifying benefits, savings, cost avoidance and/or the reduction in energy demand and usage derived from the implementation of demand side management and energy efficiency programs.  This effort will include demand side response, energy efficiency programs and metering, including the 'curtailment service provider' program.
Status:  Underway
	
	Joint WEQ/REQ DSM Subcommittee

	
	a.
	Develop matrix and business practice standards for measurement and verification for demand response products and services in ISO/RTO footprint areas.

Status: Completed 
	4th Q, 2008
	WEQ Section of the Joint WEQ/REQ DSM Subcommittee

	
	b.
	Develop more detailed technical standards for the measurement and verification of demand response products and services in ISO-RTO footprint areas. 

Status: Underway
	Phase 2
	WEQ Section of the Joint WEQ/REQ DSM Subcommittee

	
	c.
	Develop preamble for business practice standards for measurement and verification for demand response and energy efficiency programs.

Status:  Underway
	3rd Q, 2009
	Joint WEQ/REQ DSM Subcommittee

	
	d.
	Develop glossary for business practice standards 

Status:  Underway
	3rd  Q, 2009
	Joint WEQ/REQ DSM Subcommittee

	
	e.
	Support retail development of matrix and model business practice standards for measurement and verification for demand response programs 

Status:  Underway
	3rd Q, 2009
	Retail Section of the Joint WEQ/REQ DSM Subcommittee

	
	f.
	Develop business practice standards to measure and verify energy reductions that are made to comply with a Renewable Portfolio Standard that included energy efficiency or a stand-alone Energy Efficiency Portfolio Standard. 
Status: Not Started (Scope to be initiated in 2nd Q, 2009, after which a completion date will be set)
	Phase 2(
	WEQ Section of the Joint WEQ/REQ DSM Subcommittee

	
	g.
	Develop business practice standards to factor Demand Control and Energy Efficiency programs into reliability / supply decisions at the wholesale level for generation and transmission planning and operations.
Status: Not Started (Scope to be initiated in 2nd Q, 2009, after which a completion date will be set)
	Phase 2*
	WEQ Section of the Joint WEQ/REQ DSM Subcommittee

	
	h.
	Develop business practice standards to support cap and trade programs for green house gas.

Status: Not Started (Scope to be initiated in 2nd Q, 2009 at the earliest. Upon conclusion of the scoping statement it will be determined whether NAESB standards development is appropriate)
	Phase 2*
	Joint WEQ/REQ DSM Subcommittee

	7.
	Revise the Trading Partner Agreement TPA by removing the Exhibits from the agreement and relegate such information as contained in the Exhibits to operational worksheet(s), (R08015).
Status:  Complete
	2nd Q, 2009
	Joint Retail/WGQ Contracts 

	8.
	Billing and Payments
	
	

	
	a.
	Develop Process Flows to be included as models in book 3 – billing and payments

Status:  Underway
	3rd Q, 2009
	BPS

	
	b.
	If the development of Process Flows indicate a gap in the model business practices, then develop new model business practices to address the gap.

Status:  Underway
	3rd Q, 2009
	BPS

	9.
	Model Business Practices User Guide

Add a new section to Book 0 to describe what Books have been developed, how the Books are laid out, and revised the title of the Book to reflect the additions

Status: Not Started
	4th Q, 2009
	BPS

	10.
	Additional Registration Agent Processes
	
	

	
	a.
	Review all existing Model Business Practices to determine if the Service Request process is already covered, and if necessary develop any new Model Business Practices required

Status: Underway
	4th Q, 2009
	BPS

	
	b.
	Review all existing Model Business Practices to determine if the update Customer Information process is already covered, and if necessary develop any new Model Business Practices required

Status: Underway
	4th Q, 2009
	BPS

	
	c.
	Review all existing Model Business Practices to determine if the disconnection and reconnection process is already covered, and if necessary develop any new Model Business Practices required.

Status: Underway
	4th Q, 2009
	BPS

	
	d.
	Review all existing Model Business Practices to determine if the billing & payment process is already covered, and if necessary develop any new Model Business Practices required

Status: Underway
	4th Q, 2009
	BPS

	11.
	Supplier Certification

Review Book 1 – Market Participant Interactions to determine if Supplier Certification is fully covered, and if necessary develop any new Model Business Practices required with the potential of moving all related Model Business Practices to a new Book

Status: Not Started
	4th Q, 2009
	BPS

	12.
	Supplier Marketing Practices

Develop Model Business Practices providing for a “Consumer Disclosure Statement” to be presented to residential and small commercial customers describing the Supplier’s service offering and related contract provisions.  This statement would also identify how certain Supplier-Customer interactions are conducted.

Amongst the topics to be considered for inclusion on the statement would be the following:

• the most important terms of the Supplier agreement, such as the contract’s term and termination fee provisions;

• training and identification of Supplier marketing representatives;

• protocols for Supplier in-person and telephone contacts with customers;

• added measures for protecting non-English speaking customers; and

• Processes for handling customer complaints and resolving disputes arising from Supplier marketing activities.

Status:  Not Started
	4th Q, 2009
	BPS

	Program of Standards Maintenance & Fully Staffed Standards Work


	
	Business Practice Requests
	Ongoing
	Assigned  by the EC

	
	Information Requirements and Technical Mapping of Business Practices
	Ongoing
	Assigned  by the EC

	
	Ongoing Interpretations for Clarifying Language Ambiguities 
	Ongoing
	Assigned by the EC

	
	Ongoing Maintenance of Code Values and Other Technical Matters
	Ongoing
	Assigned by the EC

	
	Ongoing Development and Maintenance of Definitions
	Ongoing
	Glossary

	Provisional Activities

	
	Joint Effort:

	
	
	Supplier Certification: Develop practices for Distribution Companies to register/certify new Suppliers when they seek to begin doing business in the Distribution Company’s service area.

	
	
	Modify TPA as necessary.

	
	
	Review security standards as may be deemed necessary, such as Public Key Infrastructure (PKI).

	
	
	Review existing body of model business practices for consistency and develop or modify model business practices as needed.

	
	Retail Electric Quadrant Effort Only:

	
	
	Retail Meter Data Validation, Editing & Estimating: Develop procedures for insuring the integrity and validity of retail customer metering data that is needed by utilities and suppliers for billing, etc. Issues related to unbundled or competitive metering are not to be considered.

	
	
	Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market.  Note: will need to be coordinated with the WEQ for the REQ.

	
	Retail Gas Quadrant Effort Only:

	
	
	Examine Wholesale Gas Quadrant Non-EDM Standards for applicability to retail business practices. 

	
	
	Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market.  



[image: image1]NAESB Retail Subcommittee Leadership: 

Executive Committee:  Mike Novak, Chair (RGQ), Ruth Kiselewich, Chair (REQ)
Business Practices Subcommittee:  Phil Precht (RGQ), Mary Edwards and Dan Jones (REQ)
Information Requirements Subcommittee: Jennifer Teel (REQ)
Technical Electronic Implementation Subcommittee: TBD
Glossary Subcommittee:  Don Sytsma (RGQ), Mary Edwards and Patrick Eynon (REQ)

DSM-EE Subcommittee: Ruth Kiselewich, David Koogler (REQ), Roy True (WEQ), and Paul Wattles (WEQ)
Retail Ad Hoc Texas Task Force: Debbie McKeever (REQ), Jennifer Teel (REQ), and Susan Munson (REQ)
(*)  The Retail Ad Hoc Texas Task Force may draft MBPs, process flows, implementation guides and technical standards supportive of the Registration Agent.












Information Requirements Subcommittee (IR)











Joint Retail/WEQ DSM-EE Subcommittee








Technical 


Standards


Development





Task Forces & Working Groups








Model Business


Practice


Development





Technical Electronic 


Implementation Subcommittee (TEIS)





Retail Ad Hoc Texas Task Force (*)








Glossary Subcommittee








Contracts Subcommittee (dormant)








Business Practices Subcommittee (BPS)





Retail Electric & Retail Gas 


Quadrant Executive Committees


(REQ and RGQ ECs)








( These items may be moved to Provisional Activities





Retail 2009 Annual Plan End Notes:


� As outlined in the NAESB Bylaws, the REQ and RGQ will also address requests submitted by members and assigned to the REQ and RGQ through the Triage Process.


� Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.


� The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the annual plan document.


� The DSM-EE subcommittee is expected to be split into several separate subcommittees to support concurrent development of separate standards sets.  The split is to take place at the end of May after which the assignments will be modified.


� This work is considered routine maintenance and thus the items are not separately numbered. The REQ and RGQ ECs will assign maintenance efforts on a request-by-request basis.


� The ECs and the subcommittees can create task forces and working groups to support their development activities for development of model business practices and technical standards.








NAESB REQ/RGQ 2009 Annual Plan Adopted by the NAESB Board of Directors on March 26, 2009

with Suggested Retail EC Changes as of May 13, 2009 as expected on June 25, 2009
Page 1 of 6
NAESB REQ/RGQ 2009 Annual Plan Adopted by the NAESB Board of Directors on March 26, 2009

with Suggested Retail EC Changes as of May 13, 2009 as expected on June 25, 2009
Page 3 of 6

