## Open Parking Lot Items
Issue No. | Status | Standard | Description | Assignment | Assigned To | Meeting Date Due | Discussion/Determination
1 | Open |  | Impact and obligations to Canadian entities. Is there a need to specifically address requirements applicable to these entities?
2 | Open | 1.5 | Establishment of rules for prioritization of generation-to-load (Methods to Submit Intra-BA Transactions to the ECC) | Draft initial language for consideration | A. Watkins | 2025-04-16
3 | Open | 1.7.1 | Additional discussion and education on 1.7.1 Credit for Redispatch | Provide presentation on process used by the Eastern Interconnection | R. Thappetaobula | 2025-05-16
4 | Open | 1.7.2 | Add additional language to clarify the data used | Draft initial language for consideration | A. Watkins | 2025-04-16 | Should this additional detail be included in a functional spec document from OATI?
5 | Open | 1.8 | Develop initial language to establish rules for consolidating BAAs into Market Areas (Consolidating of BAAs) | Draft initial language for consideration | A. Watkins | 2025-04-16
6 | Open | 3.3 | Develop additional language for inclusion in 3.3 to clarify that relief obligations are made on a pro-rata basis by priority bucket | Draft initial language for consideration | A. Watkins | 2025-04-16 | Added language to section 3.3.2.1 is this sufficient?
7 | Open | 3.3.2.4 | Develop additional language for 3.3.2.4 to sufficiently outline how intra-hour tags are handled | Draft initial language for consideration | A. Watkins | 2025-04-16 | Language modified. Does the group agree with this?
8 | Open | 3.1 and 3.5 | Revise language to include notification for event start/end to entities beyond RCs, including BAs and transmisison service providers | Draft initial language for consideration | A. Watkins | 2025-04-16 | Wouldn't TSPs see this in WebTrans? What notification to BA's need and how would this comunicationt take place? RCIS, RCOMM/GIS
9 | Open | 1.3 and 1.3.1 | Determine if ECC will provide log similar to TLR log in IDC and revise Access to WERL Logs if needed
10 | Open | 1.5.1.1 | Determine if revisions are needed to Initial BA Declaration based on ECC model update functionality
11 | Open | 000-2 | Develop definitions for new defined terms