## Open Parking Lot Items
Issue No. | Status | Standard | Description | Assignment | Assigned To | Meeting Date Due | Discussion/Determination
1 | Open |  | Impact and obligations to Canadian entities. Is there a need to specifically address requirements applicable to these entities? | Provide feedback in this area for the next meeting | A. Watkins | 2025-05-16 | 4/16/2025 - Discussed during the meeting and there will be further discussion during the next meeting based on input from subject matter experts
2 | Open | 1.5 | Establishment of rules for prioritization of generation-to-load (Methods to Submit Intra-BA Transactions to the ECC) | Draft initial language for consideration | A. Watkins | 2025-05-16 | 4/16/2025 - Draft language will be provided in advance of the next meeting for review and discussion
3 | Open | 1.7.1 | Additional discussion and education on 1.7.1 Credit for Redispatch | Provide presentation on process used by the Eastern Interconnection | R. Thappetaobula | 2025-05-16
4 | Open | 1.7.2 | Add additional language to clarify the data used | Provide update on development of functional specification | A. Watkins | 2025-05-16 | 4/16/25 - Participants discussed that this could be better addressed through a functional specification that could provide the technical details of information exchange requirements
5 | Open | 1.8 | Develop initial language to establish rules for consolidating BAAs into Market Areas (Consolidating of BAAs) | Draft initial language for consideration | A. Watkins | 2025-05-16 | 4/16/25 - Draft language will be provided in advance of the next meeting for review and discussion
7 | Open | 3.3.2.4 | Develop additional language for 3.3.2.4 to sufficiently outline how intra-hour tags are handled | Provide additional revisions | A. Watkins | 2025-05-16 | 4/16/2025 - WG reviewed the revised language and discussed the need for further clarity to more closely mirror how UFMP addresses intra-hour curtailments
7 | Open | 3.3.2.4 | Develop additional language for 3.3.2.4 to sufficiently outline how intra-hour tags are handled | Provide documentation regarding BPA business practices that address intra-hour tags | R. Chung | 2025-05-16
8 | Open | 3.1 and 3.5 | Revise language to include notification for event start/end to entities beyond RCs, including BAs and transmisison service providers | Develop further revisions to provide additional details and clarity | A. Watkins | 2025-05-16 | 4/16/2025 - Participants reviewed the revised language and discussed the need for additional clarity regarding what information is to be provided as part of the notices and and to which entities
9 | Open | 1.3 and 1.3.1 | Determine if ECC will provide log similar to TLR log in IDC and revise Access to WERL Logs if needed |  |  | 2025-05-16 | 4/16/2025 - Participants discussed that this action item can be addressed with Action Item 8
10 | Open | 1.5.1.1 | Determine if revisions are needed to Initial BA Declaration |  |  |  | 4/16/2025 - Participants discussed that this is an area which will need additional feedback from industry participants
11 | Open | 000-2 | Develop definitions for new defined terms (Market Area, Production Network Model, WELR, WELR Transaction Deadline) | Provide draft language for consideration | A. Watkins | 2025-05-16
12 | Open | 2.2 | Standards language needs to address the classification of interchange transactions that will be curtailed when unclear if a constrained facility or constrained flowgate is on a particular contract path | Provide draft language for consideration | A. Watkins | 2025-05-16

## Closed Parking Lot Items
Issue No. | Status | Standard | Description | Assignment | Assigned To | Meeting Date Due | Discussion/Determination
6 | Completed | 3.3 | Develop additional language for inclusion in 3.3 to clarify that relief obligations are made on a pro-rata basis by priority bucket | Draft initial language for consideration | A. Watkins | 2025-04-16 | 4/16/2025 - WG reviewed the revised language for 3.3.2.1 and determined that no additional changes are needed at this time