## Sheet1
WEQ OASIS Subcommittee Parking Lot
API / Request | Issue No. | Status (Open, Hold, Closed) | Progress (Not Started, In Progress, Complete) | Subject | Description | Assigned To | Dates |  |  | Notes
[7 empty] | Assigned | Due | Addressed
2026 WEQ API 2.b | 1 | Open | Complete | Redirects | Create white paper for discussion at next meeting regarding preemption and redirets | Jason Williams | 2026-03-24 | 2026-04-14 | 2026-04-14 | Participants agreed to consider modifications to address first issue from work paper and potential minor corrections to address second and third issues
|  | Open | In Progress | Redirects | Create standard modifications for consideration by subcommittee | Jason Williams | 2026-04-14 | 2026-05-12
|  | Open | In Progress | NERC References | Identify any potential modifications that are needed | Rob Arbitelle & John Marhoefer | 2026-04-14 | 2026-05-12
R26004 |  | Open | In Progress | Pro/Con List for Field Length Adjustments | Create work paper documenting pros/cons to identify any changes needed | Subcommittee | 2026-04-14 | 2026-05-12