## WEQ BPS
Business Practices Subcommittee Action Items
Issue # | Status | Description | Assigned to | Dates
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed | Notes
Next Number to assign - 2

## OASIS-BPS Assignments
OASIS/BPS Subcommittee Action Items
API (year) | Issue # | Status (Open Closed Hold) | Progress (Completed Not Started In Progress) | Description | Assigned to | Dates |  |  | Notes
[6 empty] | Assigned | Due | When Addressed | Notes
2.a.i.1 (2018) | 1 | Closed | Completed | Comparison of existing OASIS templates vs FERC ORDER 890 – Posting of additional information on OASIS regarding firm transmission curtailments | R Berdahl (BPA) [R Arbitelle (Southern)] | OS: 11/2017 | OS/BPS: 01/2018 | OS/BPS: 01/2018
2.a.i.1 (2018) | 2 | Closed | Completed | How to document TLR events in the OASIS templates and any deficiencies | P Sorenson (OATI) | OS: 11/2017 | OS/BPS: 01/2018 | OS/BPS: 01/2018
2.a.i.2 (2018) | 1 | Closed | Completed | Draft a Recommendation for Redispatch Cost Posting to allow for posting of third party offers of planning redispatch services | A. Pritchard (Duke) [Sorenson(OATI)] | OS: 10/2017 |  | OS: 11/2017 | Draft recommendation completed and has been voted out for informal comment
3.a (2017) | 1 | Closed | Completed | Draft a no action recommendation for The outstanding item is Enhance the TSR result postings to allow showing of available generation dispatch options that would allow acceptance of reservation request. | JT Wood (SOCO) | OS: 10/2017 |  | OS/BPS: 11/2017 | Recommendation voted out for formal comment
3.b (2017) | 1 | Closed | Completed | Draft a no action recommendation for Enhance the TSR Results posting to allow a showing of limiting transmission elements for denied transmission service requests. R05026 scoping statement completed by SRS. | JT Wood (SOCO) | OS: 11/2017 |  | OS/BPS: 11/2017 | Recommendation voted out for formal comment
2.a.i.1 (2018) | 3 | Open | In Progress | Provide review of Order 890 comments and documentation associated with para 1627 | A. Prichard (Duke) | OS/BPS: 01/2018 | OS/BPS: 02/2018 | OS/BPS: 02/2018
2.a.i.2 (2018) | 2 | Closed | Completed | Combine informal comments into Draft Recommendation for Redispatch Cost Posting to allow for posting of third party offers of planning redispatch services | JT Wood (SOCO) | OS/BPS: 01/2018 | OS/BPS: 01/2018 | OS/BPS: 01/2018 | Recommendation voted out for formal comment

## BPS_OS Joint Open
Joint Business Practices Subcommittee and OASIS Action Items
Issue # | Status | Description | Assigned to | Dates
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed | Notes

## Joint Closed
Joint Business Practices Subcommittee and OASIS Action Items
Issue # | Status | Description | Assigned to | Dates
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed | Notes
1 | Closed | Review what information is available on the events and circumstances contributing to the curtailment of firm service and customers curtailed, including the transmission provider's own retail load and the duration of the curtailment (AP Item 2.a.ii.1) | BPS |  |  | 2016-06-07 | 10/6/15 - Created work paper but before finalizing need additional input from customers 6/7/16 - This item was completed through Action Item 11
2 | Closed | What information is needed to comply with FERC requirements for additional data postings for the benefit of customers and auditors. (AP Item 2.a.ii.1) | BPS |  |  | 2016-06-07 | 10/6/15 - Created work paper but before finalizing need additional input from customers 6/7/16 - This item was completed through Action Item 11
3 | Closed | What information is publically available in the IDC for the Eastern Interconnection and the USF (unscheduled flow) procedures in the WECC (AP Item 2.a.ii.1) | BPS |  |  | 2016-06-07 | 10/6/15 - IDC currently doesn't make information available publically. Also, IDC doesn't know the reason congestion is occuring 6/7/16 - This item was completed through Action Item 11
4 | Closed | What is meant by planning redispatch? Is it only long-term? Is it only firm? Etc. Order 890, Paragraph 901+ (AP Item 2.a.ii.2) | BPS |  |  |  | 12/1/15 - BPS determined that third party offers are for planning redispatch which is for long-term firm
5 | Closed | What information is needed from third parties for planning redispatch that will satisfy requirement for need for the transmission providers to implement congestion management (AP Item 2.a.ii.2) | BPS |  |  |  | 12/1/15 - BPS decided to post the generator information from third parties.
6 | Closed | How are third party offers for planning redispatch service acquired by customers? Off OASIS process? How will these arrangments be submitted to transmission providers for verification and validation? (AP Item 2.a.ii2) | BPS |  |  |  | 12/1/15 - BPS determined that third party offers are acquired by the customers of OASIS. Submission of third party offers to transmission providers will be based on the specific requirements of transmission providers
7 | Closed | Review R12006 and API 3.a.i.3 in order to identify any requirements that would be specific to SAMTS request by NITS customers (AP Item 5.e) | BPS/J. Manning |  | 2015-11-04 |  | 11/4 - New Action Item 12 created to identify any additional information
9 | Closed | What information is a transmission customer seeking on available generation dispatch options that will allow acceptance of the reservation request (AP Item 3.a.i.3) | BPS |  |  |  | 3/1/2016 - BPS agreed to forward work paper for review by OASIS Subcommittee
10 | Closed | Create a document for informal comment to solicit information on Action Items 4 - 6 | N. Saini | 2015-10-06 | 2015-12-01 | 2015-12-01 | 11/4 - Reviewed document prepared by Mr. Saini and BPS decided to further work on based on OATT requirements before posted for informal comment 12/1 - BPS decided to include generation information for third party offers for planning redispatch. No informal comments are needed.
11 | Closed | Create a document for informal comment to solicit information on Action Items 1 - 3 | J. Davis | 2015-10-06 | 2015-11-03 | 2016-06-07 | 11/4 - Will review at next meeting 12/1 - Will review during next meeting 1/5 - Reviewed during meeting and will continue to review next meeting 2/1/16 - Created Action Item16 for Western Interconnection feedback 6/7/16 - Through completing Action Items 1 - 3, BPS determined informal comments are not needed. The documentation will be forwarded to the OASIS Subcommittee.
13 | Closed | Create document for responding to AP Item 3.a.i.3 regarding redispatch options which are available through system impact studies | N. Saini | 2015-12-01 | 2016-01-05 | 2016-02-02 | 1/5/16 - Reviewed initial document and will further review during the next meeting 2/2/16 - BPS agreed to forward work paper for review by OASIS Subcommittee
14 | Closed | Create examples for discussing limiting transmission elements to be posted on OASIS for short-term firm reservations | P. Graves R. Robinson | 2015-12-01 | 2016-01-05 | 2016-01-05 | 2/2/16 - Discussed during previous meeting and issue resolved
15 | Closed | Finalize document for AP Item 2.a.ii.2 | N. Saini | 2015-12-01 | 2016-01-05 | 2016-01-05 | 1/5 - The revised document was reviewed and revised and BPS decided to forward to OASIS
16 | Closed | Develop a draft list of additional information to address AP Item 2.a.ii.1 for the Western Interconnect | B. Fung | 2016-02-02 | 2016-03-01 | 2016-05-03 | 5/3/16 - Subcommittee reviewed work paper provided by B. Fung